## 09-10 (hidden)
Physical & Financial Progress on Implementation of MPLADS works in Bangalore [Urban] District
Name of the M.P. : Sri P.C.Mohan, Hon'ble MP. Lok Sabha | [5 empty] | Year : 2009-10
Sl No | Name & Location of the work | Estimated Cost [in Lakhs] | Stage of the work | Implementing Agency | Expenditure incurred | Balance if any | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | The construction building of Astagrama Association in 1st floor at No:46, Astagrama Sanga Layout Magadi Main road, Bangalore-79 | 2.5 | completed | Nirmithi kendra | 2.5 | 0
2 | Construction of School building at Rastrothana parishath Jai Gopal Garoda Rastrothana Vidyalaya Site No: 21, 1st blopck, Kalyanagar, H.R.B.R layout, Bangalore | 15 | completed | EEPRED | 15 | 0
3 | Construction of Karnataka Chitrakala parishath building at Kumara park East, Bangalore | 5 | completed | EEPRED | 5 | 0
4 | Construction of school and hostal building of General Hostel Karnataka Thigala Samajika vidyabhivruddhi Sangha 10th main 5th block, Rajajinagar, Bangalore | 10 | completed | EEPRED | 10 | 0
5 | Construction of High School building at Mudaliyar Sena Sangha No:8, 6th cross, Prakash Nagar, Bangalore | 15 | completed | EEPRED | 15 | 0
6 | Drilling of borewell along with pump set -& P.V.C Pipeline at Rajajinagar Constituency in ward No: 101, Kamakshipalya Bangalore | 8 | completed | EEPRED | 8 | 0
7 | Drilling of Borewell along with pump set 2 P.V.C pipeline at 4th H-Block Srirama mandir ward Rajajinagar Assembly constituency | 6 | completed | EEPRED | 6 | 0
8 | Drilling of Borewell along with pump set & P.V.C pipeline at prakashnagar,Rajajinagar Assembly constituency | 9.6 | completed | EEPRED | 9.6 | 0
9 | Construction of Samudaya bhavan building nayaka community at All India Nayaka Sangha C.A.Site No:1, 11th main, 3rd stage 1st block, Basaveshwara nagar, Bangalore Taluk | 10 | completed | EEPRED | 10 | 0
10 | Construction of High tech toilets at siddaganga school premises Shivanagara ward Rajajinagar Assembly const. | 7 | completed | EEPRED | 7 | 0
11 | Construction of Samskruthika bhavan at Mahaganapathinagar, Shivanagar ward, Rajajinagar Assembly const. | 3 | completed | EEPRED | 3 | 0
12 | Construction of Samudhaya bhavan at Valepura Mahadevapura Assembly constitution Bangalore | 5 | completed | EEPRED | 5 | 0
13 | Construction of Samudhaya bhavan at Bayyappanahally Mahadevapura Assembly constitution Bangalore | 5 | completed | EEPRED | 5 | 0
14 | Construction of Samudhaya bhavan at Nimbekayipura Mahadevapura Assembly constitution Bangalore | 5 | completed | EEPRED | 5 | 0
15 | Construction of Samudhaya bhavan at Yarappanahally, Mahadevapura Assembly constitution Bangalore | 5 | completed | EEPRED | 5 | 0
16 | Construction of Burial ground [Chithagara] at Bidarahalli village, mahadevapura Assembly const. | 5 | completed | EEPRED | 5 | 0
17 | Drilling of Borewell alongwith pump set & pvc line at Banasavadi village, Bangalore | 6.2 | completed | EEPRED | 6.2 | 0
18 | Drilling of Borewell alongwith pump set & pvc line at A.K.Colony, Banasavadi ward no: 43, Bangalore | 6.2 | completed | EEPRED | 6.2 | 0
19 | Construction of hostal building of General Hostel K.I.S.V. Sanga 10th main road, 5th block, Rajajinagar, Bangalore-10 | 10 | completed | EEPRED | 10 | 0
20 | Drilling of Borewell along with pumpset and pvc pipe at 2nd A-Main road, Ramachandrapura Okalipuram,ward Gandhinagar Assembly const., Bangalore | 5.4 | completed | EEPRED | 5.4 | 0
21 | Drilling of borewell along with pumpset and Pvc pipe at cottonpet ward No: 120 T.D.Lane, Bangalore | 5 | completed | EEPRED | 5 | 0
22 | Drilling of borewell alongwith pumpset and pvc line at cottonpet ward no:120, K.P.Agrahara Main road, Bangalore | 4.3 | completed | EEPRED | 4.3 | 0
23 | Purchase of 2 computers to united mission primary and Middle school, Mission road, Bangalore-27 | 0.74124 | completed | Abhishek enterprises | 0.74124 | 0
24 | Construction of Samaloch Bhavan at Karnataka Chitrakala Parishath campus Kumarakrupa road, Bangalore | 10 | completed | EEPRED | 10 | 0
25 | Rastrothana Parishath construction of Nandagokula building at Rastrothana Parishath Site No: 2, Magadi Road, Vinayaka H.B.C.S, Bangalore | 15 | completed | EEPRED | 15 | 0
26 | Construction of Samudhaya Bhavan at Karnataka Chitrakala Parishath compound, Kumarakrupa Road, Bangalore-01 | 10 | completed | EEPRED | 10 | 0
27 | Construction at School Rooms and Toilets at Government Goys Urdu Model Primary School, J.J.R. Nagar, Bangalore | 10 | completed | EEPRED | 10 | 0
|  | 198.9412 |  |  | 198.9412 | 0
|  |  | Released from Govt. of India | Administrative sanctioned Accurded |  | Expenditure incurred | Balance
|  |  | 200 | EE PRED | 195.7 | 195.7 | 0
|  |  |  | Nirmithi Kendra | 2.5 | 2.5 | 0
|  |  |  | Other DC's |  |  | 0
|  |  |  | Abhishek Enter | 0.74 | 0.74 | 0
|  |  |  | TOTAL | 198.94 | 198.94 | 0

## 10-11 (hidden)
Physical & Financial Progress on Implementation of MPLADS works in Bangalore [Urban] District
Name of the M.P. : Sri P.C.Mohan, Hon'ble MP. Lok Sabha | [5 empty] | Year : 2010-11
Sl No | Name & Location of the work | Estimated Cost [in Lakhs] | Stage of the work | Implementing Agency | Expenditure incurred | Balance if any | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Construction of Library rooms at B.K.Mariappa Charities 3rd main road, Chamarajapet, Bangalore-18 | 5 | completed | Nirmithi kendra | 5 | 0
2 | Construction of School building at Vanitha Seva Mandira 11th block, Rajajinagar, Bangalore | 10 | completed | Nirmithi kendra | 10 | 0
3 | Construction of Food Shelter for the Students St.Xavier's High School Shivajinagar, Bangalore-51 | 10 | completed | EEPRED | 9.95 | 0.05
4 | Construction of School building Sri.Sharada Vidya Mandira, Balagere road, Varthuru, Bangalore-87 | 10 | completed | EEPRED | 9.95 | 0.05
5 | Construction of Indoor Badminton Court D-block, Rajajinagar, Nerar Sai college, Bangalore [1st stage] | 10 | completed | EEPRED | 9.95 | 0.05
6 | Construction of Indoor Badminton Court D-block, Rajajinagar, Nerar Sai college,Bangalore [2nd stage] | 10 | completed | EEPRED | 9.95 | 0.05
7 | Construction of Indoor Badminton Court D-block, Rajajinagar, Nerar Sai college, Bangalore [3rd stage] | 5 | completed | EEPRED | 4.975 | 0.025
8 | Construction of High Tech Toilets at Government High School Pallavi Talkies Backside, Sampangirama nagar, Bangalore [Stage-I] | 2.5 | completed | EEPRED | 2.4875 | 0.0125
9 | Construction of High Tech Toilets at Government High School Pallavi Talkies Backside, Sampangirama nagar, Bangalore [Stage-II] | 2.5 | completed | EEPRED | 2.4875 | 0.0125
10 | Construction of High Tech Toilets at Government High School Pallavi Talkies Backside, Sampangirama nagar, Bangalore [Stage-III] | 2.5 | completed | EEPRED | 2.4875 | 0.0125
11 | Construction of High Tech Toilets at Government High School Pallavi Talkies Backside, Sampangirama nagar, Bangalore [Stage-IV] | 2.5 | completed | EEPRED | 2.4875 | 0.0125
12 | Construction of Indoor Badminton court at 1st block, Rajajinagar near Sai college, Prakashnagar, Ward Rajajinagar Assembly constituency Bangalore | 10 | completed | EEPRED | 9.95 | 0.05
13 | Providing water pipe line and public taps works at Main and cross roads at 1] Kamakshipalya 5th and 6th cross, 7th cross roads 2] Kamakshipalya 1st , 4th 5th, 7th , 8th and 30th main roads 3] Meenakshinagar 5th, 6th 7th Main road, 4] Construction & beds to public Taps | 21.5 | completed | EEPRED | 21.3925 | 0.1075
14 | Providing piped water supply scheme and construction of one lakh litre capacity of over head Tank at Mandur village, Bidarahalli hobli, Bangalore East Taluk | 12 | completed | EEPRED | 12 | 0
15 | Construction of School Rooms in Sri.Sikddaganga School Shivanagara Ward Rajajinagar, Assembly const. | 20 | completed | EEPRED | 19.9 | 0.1
16 | Construction of Anganawadi building ward no:28, Kamanahally Sarvagnanagar Division, Bangalore | 9.5 | under progress | Nirmithi kendra | 4.75 | 4.75
17 | Constructio of School and Hostal building devanga Sangha Devanga Hostel road, S.R.Nagar, Bangalore [Stage-1] | 5 | completed | EEPRED | 4.98 | 0.02
18 | Constructio of School and Hostal building devanga Sangha Devanga Hostel road, S.R.Nagar, Bangalore [Stage-2] | 5 | completed | EEPRED | 4.98 | 0.02
19 | Construction of Anganawadi building at Flower Garden Main road, Cheluvadipalya, Ward No:138, Bangalore-18 | 19.9 | under progress | BBMP | 9.8 | 10.1
20 | Construction of High Tech Dining Hall and High Tech Library building in Karnataka Pradesh Arya Idigara Sangha -185, Idiga Bhavan 2nd floor RajeevGandhi Circle, Sheshadripuram, Bangalore | 25 | completed | Nirmithi kendra | 25 | 0
|  | 197.9 |  |  | 182.4775 | 15.4225
|  |  | Released from Govt. of India | Administrative sanctioned Accurded |  | Expenditure incurred | Balance
|  |  | 200 | EE PRED | 128.5 | 127.9275 | 0.5725
|  |  |  | Nirmithi Kendra | 49.5 | 44.75 | 4.75
|  |  |  | Other DC's |  |  | 0
|  |  |  | BBMP | 19.9 | 9.8 | 10.1
|  |  |  | TOTAL | 197.9 | 182.4775 | 15.4225
47.24

## 11-12 (hidden)
Physical & Financial Progress on Implementation of MPLADS works in Bangalore [Urban] District
Name of the M.P. : Sri P.C.Mohan, Hon'ble MP. Lok Sabha | [5 empty] | Year : 2011-12
Sl No | Name & Location of the work | Estimated Cost [in Lakhs] | Stage of the work | Implementing Agency | Expenditure incurred | Balance if any | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Construction of High Tech toilets and bath rooms in Brahmana Vidyarthi Sahaya Sangha Sheshadripuram, Bangalore-20 | 5 | completed | Nirmithi kendra | 5 | 0
2 | Construction of Two Library rooms at Govt. P.u.College Varthuru Mahadevapura Assembly const. | 10 | completed | Nirmithi kendra | 10 | 0
3 | Supply of Computers and printersd to Nau Bahar Shah School, [Govt. Aided school] No:140, Mackane road, Bharathinagar, Bangalore-1 | 3.044 | completed | Maruthi computers Enterprises | 3.04 | 0.00395
4 | Construction of Senior Citizen Bhavana Ward no: 58, New Thippasandra HAL 3rd stage C.V.Raman nagara const.[1st stage] | 10 | completed | EEPRED | 10 | 0
5 | Construction of Senior Citizen Bhavana Ward no: 58, New Thippasandra HAL 3rd stage C.V.Raman nagara const.[2nd stage] | 10 | completed | EEPRED | 10 | 0
6 | Construction of Stri Shakthi Bhavan Ward No: 58, New Thippasandra HAL 3rd stage C.V.Raman Nagar, Const.[Stage-1] | 10 | completed | EEPRED | 10 | 0
7 | Construction of Stri Shakthi Bhavan Ward No: 58, New Thippasandra HAL 3rd stage C.V.Raman Nagar, Const.[Stage-2] | 10 | completed | EEPRED | 10 | 0
8 | Construction of Sanskruthi Bhavan of Kannada Sanskruthi mahila Koota, Ward No: 58, New Thippasandra HAL 3rd stage C.V.Raman Nagar, Const. | 10 | completed | EEPRED | 10 | 0
9 | Drilling of 2 Borewell along with pumpset and PVC pipelines at 1] Govindapura Ward 2] Hennur Garden H.B.R. Layout | 11 | under progress | EEPRED | 0 | 11
10 | Construction of Class rooms at B.B.M.P Urdu School Jagjeevanram nagar, Chamarajapet Assembly const. | 2.5 | completed | EEPRED | 2.5 | 0
11 | Construction of office room at B.B.M.p Urdu School J.J.R. Nagar Ward no:137, Chamarajapet Assembly const.-1 | 2.5 | completed | EEPRED | 2.5 | 0
12 | Construction of office room at B.B.M.p Urdu School J.J.R. Nagar Ward no:137, Chamarajapet Assembly const.-2 | 2.5 | completed | EEPRED | 2.5 | 0
13 | Construction of Staged Urinals block B.B.M.p Urdu school J.J.R. nagar ward No: 137, Chamarajpet Assembly const. | 2.5 | completed | EEPRED | 2.5 | 0
14 | Additional construction of class rooms at new fort-school and college Pampa mahakavi road, Ward No: 140, Chamarajpet Assembly const. | 2.5 | completed | EEPRED | 2.5 | 0
15 | Construction of class rooms at new fort college Pampa mahakavi road, Ward No: 140, Chamarajpet Assembly const. | 2.5 | completed | EEPRED | 2.5 | 0
16 | Construction of Library room at new fort-school and college Pampa mahakavi road, Ward No: 140, Chamarajpet Assembly const. | 2.5 | completed | EEPRED | 0 | 2.5
17 | Construction of Laboratory at new fort-school and college Pampa mahakavi road, Ward No: 140, Chamarajpet Assembly const. | 2.5 | completed | EEPRED | 0 | 2.5
18 | Construction of Staff room at new fort-school and college Pampa mahakavi road, Ward No: 140, Chamarajpet Assembly const. | 2.5 | completed | EEPRED | 0 | 2.5
19 | Construction of Rangamantapa katamnallur Mahadevapura Assembly const. | 5 | Estimated awaited | EEPRED | 0 | 5
20 | Construction of School compound at Bldave Agrahara Mahadevapura Assembly const. | 5 | Estimated awaited | EEPRED | 0 | 5
21 | Construction of Ambedkar bhavan Mandura, Mahadevapura Assembly const. | 10 | Estimated awaited | EEPRED | 0 | 10
22 | Construction of Sri.Samavasha Sahasarjuna Skshathriya Samaja Hostel Sheshadripuram, Banglaore | 15 | completed | EEPRED | 15 | 0
23 | Construction of School hostel building and Auditorium Kumarakrupa Road, Bangalore | 10 | Estimated awaited | EEPRED | 0 | 10
24 | Construction of Aduditorium and Hitech library building at no: 19 , Yadava Sangha H>R.B.R Extn, Banasavadi Main Road, Bangalore | 25 | under progress | EEPRED | 12.5 | 12.5
25 | Costruction of Hitech library building bangalore Thamil Sangham Mudaliar road, Shivajinagar, Bangalore | 16.7 | completed | EEPRED | 16.7 | 0
26 | Construction of Govt. Junior Primary Scbhool at ward No: 58 Byrasandra C.V.Raman nagar Ass. Const [Stage-1] | 10 | under progress | EEPRED | 0 | 10
27 | Construction of Govt. Junior Primary Scbhool at ward No: 58 Byrasandra C.V.Raman nagar Ass. Const [Stage-2] | 10 | under progress | EEPRED | 0 | 10
28 | Construction of New Kalyani and developmental works at ward No: 80 Maramma devi temple at Hoysalanagar, C.V.Raman nagar Const. Bangalore [Stage-1] | 10 | completed | EEPRED | 10 | 0
29 | Construction of New Kalyani and developmental works at ward No: 80 Maramma devi temple at Hoysalanagar, C.V.Raman nagar Const. Bangalore [Stage-2] | 10 | completed | EEPRED | 10 | 0
30 | Construction of New Kalyani and developmental works at ward No: 80 Maramma devi temple at Hoysalanagar, C.V.Raman nagar Const. Bangalore [Stage-3] | 10 | completed | EEPRED | 10 | 0
31 | Construction of New Kalyani and developmental works at ward No: 80 Maramma devi temple at Hoysalanagar, C.V.Raman nagar Const. Bangalore [Stage-4] | 10 | completed | EEPRED | 10 | 0
32 | Construction of Devanga Sangha college building Devaga Hostel road, S.R.Nagar, Bangalore | 15 | completed | Nirmithi kendra | 15 | 0
33 | Drilling of borewell at venkataram nagar ward no:140, and 141, Valmikinagar Bangalore | 5.35 | completed | EEPRED | 5.35 | 0
34 | Providing submercible pump, panel borard, overhead tank, pipes and taps at venkataram nagar ward no:140, and 141, Valmikinagar Bangalore | 5.35 | completed | EEPRED | 5.35 | 0
35 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps at - Salappa Layout Ward No: 137, Bangalore | 5.35 | completed | EEPRED | 5.35 | 0
36 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps at - Padarayana palya Ward No: 138, Bangalore | 5.35 | completed | EEPRED | 5.35 | 0
37 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps at -Ranasinghpet Ward No: 139, Bangalore | 5.35 | completed | EEPRED | 5.35 | 0
38 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps at -Ramaswamy Palya Ward No: 28, Bangalore | 5.35 | Estimated awaited | EEPRED | 0 | 5.35
39 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps at -Subbaiah Palya Ward No: 28, Bangalore | 5.35 | Estimated awaited | EEPRED | 0 | 5.35
40 | Providing water tank and pipeline at Sri.Raman Mandira, 4th m-block, 59-c cross, Ward No: 108 Bangalore | 5 | Estimated awaited | EEPRED | 0 | 5
41 | Construction of three class rooms at 2nd floor at Govt Urdu Primary and English High School, Bangalore Ward No: 137 | 15.7 | Estimated awaited | EEPRED | 0 | 15.7
42 | Construction of Auditorium at 3rd floor at Govt Urdu Primary and English High School, Bangalore Ward No: 138 | 12.5 | Estimated awaited | EEPRED | 0 | 12.5
43 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps being at Nagavara Govt School Ward No: 24, Sc/ST colony, Bangalore | 5.35 | completed | EEPRED | 5.35 | 0
44 | Construction of Anganwadi building and computer centre ground floor and first floor at K.G.Halli, wardNo; 30 Bangalore | 17 | completed | EEPRED | 17 | 0
45 | Construction of hitech library building at ward No; 108, Sri.Vitala Mandira Trust, # 691, 45 cross, 3rd block, Rajajinagar, Bangalore-10 | 10 | completed | EEPRED | 10 | 0
46 | Civil construction of Dormitary at Bal. Bhavan Premises cubbon park, Bangalore | 25 | completed | EEPRED | 25 | 0
47 | Construction of Modern Smart class rooms at Terrace area ward No: 49, Dr. Chandrashekar Institute of Speech and hearing Hennur road, Lingarajapuram, Bangalore | 12.5 | completed | Nirmithi kendra | 12.5 | 0
48 | Construction of rooms in Gandhi vidya school ward No: 97, Dayanandanagar, Srirampura, Bangalore | 20 | completed | EEPRED | 20 | 0
49 | Construction of 3 class rooms at I.M.N.Govt aided school, ward No: 91, Bangalore | 17 | completed | EEPRED | 17 | 0
50 | Installing grills to N.B.S. Govt primary and High school, Kackan Road, Ward no: 80, Bangalore | 2 | completed | EEPRED | 2 | 0
51 | Construction of toilets at ward No: 110, city civil court Shivajinagar, Bangalore | 10 | completed | EEPRED | 10 | 0
|  | 452.744 |  |  | 327.84 | 124.9039
|  |  | Released from Govt. of India | Administrative sanctioned Accurded |  | Expenditure incurred | Balance
|  |  | 500 | EE PRED | 407.2 | 282.3 | 124.9
|  |  |  | Nirmithi Kendra | 42.5 | 42.5 | 0
|  |  |  | BBMP | 0 | 0 | 0
|  |  |  | Maruthi Computers | 3.044 | 3.04 | 0.00395
|  |  |  | TOTAL | 452.744 | 327.84 | 124.904

## Full Details (hidden)
Sl.No. | name mla/mlc | name of constistuency | year | work details | sanctioned amt | implementing agency | amt released to I.A | stage of work | Balance
1 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of Indian Medical Association building at IMA House Alur Venkatarao road near IMA circle, Bangalore | 2.5 | EEPRED | 0 | under progress | 2.5
2 | P.C.Mohan | M.P, Lokasabha | 2009-10 | The construction building of Astagrama Association in 1st floor at No:46, Astagrama Sanga Layout Magadi Main road, Bangalore-79 | 2.5 | Nirmithi kendra | 2.4875 | completed | 0.0125
3 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of School building at Rastrothana parishath Jai Gopal Garoda Rastrothana Vidyalaya Site No: 21, 1st blopck, Kalyanagar, H.R.B.R layout, Bangalore | 15 | EEPRED | 14.9225 | completed | 0.0775
4 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of Karnataka Chitrakala parishath building at Kumara park East, Bangalore | 5 | EEPRED | 4.975 | completed | 0.025
5 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of school and hostal building of General Hostel Karnataka Thigala Samajika vidyabhivruddhi Sangha 10th main 5th block, Rajajinagar, Bangalore | 10 | EEPRED | 9,94,500 | completed | -994490
6 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of High School building at Mudaliyar Sena Sangha No:8, 6th cross, Prakash Nagar, Bangalore | 15 | EEPRED | 14.925 | completed | 0.075
7 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Drilling of borewell along with pump set -& P.V.C Pipeline at Rajajinagar Constituency in ward No: 101, Kamakshipalya Bangalore | 8 | EEPRED | 7.96 | completed | 0.04
8 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Drilling of Borewell along with pump set 2 P.V.C pipeline at 4th H-Block Srirama mandir ward Rajajinagar Assembly constituency | 6 | EEPRED | 5.97 | completed | 0.03
9 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Drilling of Borewell along with pump set & P.V.C pipeline at prakashnagar,Rajajinagar Assembly constituency | 9.6 | EEPRED | 9.55 | completed | 0.05
10 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of Samudaya bhavan building nayaka community at All India Nayaka Sangha C.A.Site No:1, 11th main, 3rd stage 1st block, Basaveshwara nagar, Bangalore Taluk | 10 | EEPRED | 9.95 | completed | 0.05
11 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of High tech toilets at siddaganga school premises Shivanagara ward Rajajinagar Assembly const. | 7 | EEPRED | 6.965 | completed | 0.035
12 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of Samskruthika bhavan at Mahaganapathinagar, Shivanagar ward, Rajajinagar Assembly const. | 3 | EEPRED | 2.985 | completed | 0.015
13 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of Samudhaya bhavan at Valepura Mahadevapura Assembly constitution Bangalore | 5 | EEPRED | 5 | completed | 0
14 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of Samudhaya bhavan at Bayyappanahally Mahadevapura Assembly constitution Bangalore | 5 | EEPRED | 4.975 | completed | 0.025
15 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of Samudhaya bhavan at Nimbekayipura Mahadevapura Assembly constitution Bangalore | 5 | EEPRED | 2,48,750 | completed | -248745
16 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of Samudhaya bhavan at Yarappanahally, Mahadevapura Assembly constitution Bangalore | 5 | EEPRED | 4.975 | completed | 0.025
17 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of Burial ground [Chithagara] at Bidarahalli village, mahadevapura Assembly const. | 5 | EEPRED | 4.975 | completed | 0.025
18 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of Yathri nilaya at Thirupathi Thirumala, Bangalore | 10 | EEPRED | 0 | under progress | 10
19 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Drilling of Borewell alongwith pump set & pvc line at Banasavadi village, Bangalore | 6.2 | EEPRED | 6.169 | completed | 0.031
20 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Drilling of Borewell alongwith pump set & pvc line at A.K.Colony, Banasavadi ward no: 43, Bangalore | 6.2 | EEPRED | 6.169 | completed | 0.031
21 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Construction of hostal building of General Hostel K.I.S.V. Sanga 10th main road, 5th block, Rajajinagar, Bangalore-10 | 10 | EEPRED | 9.95 | completed | 0.05
22 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Drilling of Borewell along with pumpset and pvc pipe at 2nd A-Main road, Ramachandrapura Okalipuram,ward Gandhinagar Assembly const., Bangalore | 5.4 | EEPRED | 5.3725 | completed | 0.0275
23 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Drilling of borewell along with pumpset and Pvc pipe at cottonpet ward No: 120 T.D.Lane, Bangalore | 5 | EEPRED | 4.975 | completed | 0.025
24 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Drilling of borewell alongwith pumpset and pvc line at cottonpet ward no:120, K.P.Agrahara Main road, Bangalore | 4.3 | EEPRED | 4.275 | completed | 0.025
25 | P.C.Mohan | M.P, Lokasabha | 2009-10 | Purchase of 2 computers to united mission primary and Middle school, Mission road, Bangalore-27 | 0.74124 | Abhishek enterprises | 0.74124 | completed | 0
26 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of Samaloch Bhavan at Karnataka Chitrakala Parishath campus Kumarakrupa road, Bangalore | 10 | EEPRED | 9.95 | completed | 0.05
27 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Rastrothana Parishath construction of Nandagokula building at Rastrothana Parishath Site No: 2, Magadi Road, Vinayaka H.B.C.S, Bangalore | 15 | EEPRED | 7.5 | under progress | 7.5
28 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of Samudhaya Bhavan at Karnataka Chitrakala Parishath compound, Kumarakrupa Road, Bangalore-01 | 10 | EEPRED | 9.95 | completed | 0.05
29 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction at School Rooms and Toilets at Government Goys Urdu Model Primary School, J.J.R. Nagar, Bangalore | 10 | EEPRED | 4.975 | under progress | 5.025
30 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of Library rooms at B.K.Mariappa Charities 3rd main road, Chamarajapet, Bangalore-18 | 5 | Nirmithi kendra | 2.4875 | under progress | 2.5125
31 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of School building at Vanitha Seva Mandira 11th block, Rajajinagar, Bangalore | 10 | Nirmithi kendra | 4.98 | under progress | 5.02
32 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of Food Shelter for the Students St.Xavier's High School Shivajinagar, Bangalore-51 | 10 | EEPRED | 9.95 | completed | 0.05
33 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of School building Sri.Sharada Vidya Mandira, Balagere road, Varthuru, Bangalore-87 | 10 | EEPRED | 9.95 | completed | 0.05
34 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of Indoor Badminton Court D-block, Rajajinagar, Nerar Sai college, Bangalore [1st stage] | 10 | EEPRED | 9.95 | completed | 0.05
35 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of Indoor Badminton Court D-block, Rajajinagar, Nerar Sai college,Bangalore [2nd stage] | 10 | EEPRED | 9.95 | completed | 0.05
36 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of Indoor Badminton Court D-block, Rajajinagar, Nerar Sai college, Bangalore [3rd stage] | 5 | EEPRED | 4.975 | completed | 0.025
37 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of High Tech Toilets at Government High School Pallavi Talkies Backside, Sampangirama nagar, Bangalore [Stage-I] | 2.5 | EEPRED | 2.4875 | completed | 0.0125
38 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of High Tech Toilets at Government High School Pallavi Talkies Backside, Sampangirama nagar, Bangalore [Stage-II] | 2.5 | EEPRED | 2.4875 | completed | 0.0125
39 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of High Tech Toilets at Government High School Pallavi Talkies Backside, Sampangirama nagar, Bangalore [Stage-III] | 2.5 | EEPRED | 2.4875 | completed | 0.0125
40 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of High Tech Toilets at Government High School Pallavi Talkies Backside, Sampangirama nagar, Bangalore [Stage-IV] | 2.5 | EEPRED | 2.4875 | completed | 0.0125
41 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of Indoor Badminton court at 1st block, Rajajinagar near Sai college, Prakashnagar, Ward Rajajinagar Assembly constituency Bangalore | 10 | EEPRED | 9.95 | completed | 0.05
42 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Providing water pipe line and public taps works at Main and cross roads at 1] Kamakshipalya 5th and 6th cross, 7th cross roads 2] Kamakshipalya 1st , 4th 5th, 7th , 8th and 30th main roads 3] Meenakshinagar 5th, 6th 7th Main road, 4] Construction & beds to public Taps | 21.5 | EEPRED | 21.3925 | completed | 0.1075
43 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Providing piped water supply scheme and construction of one lakh litre capacity of over head Tank at Mandur village, Bidarahalli hobli, Bangalore East Taluk | 19 | EEPRED | 12 | under progress | 7
44 | P.C.Mohan | M.P, Lokasabha | 2010-11 | Construction of School Rooms in Sri.Sikddaganga School Shivanagara Ward Rajajinagar, Assembly const. | 20 | EEPRED | 19.9 | completed | 0.1
45 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Anganawadi building ward no:28, Kamanahally Sarvagnanagar Division, Bangalore | 9.5 | Nirmithi kendra | 4.75 | under progress | 4.75
46 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Constructio of School and Hostal building devanga Sangha Devanga Hostel road, S.R.Nagar, Bangalore [Stage-1] | 5 | EEPRED | 4.98 | completed | 0.02
47 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Constructio of School and Hostal building devanga Sangha Devanga Hostel road, S.R.Nagar, Bangalore [Stage-2] | 5 | EEPRED | 4.98 | completed | 0.02
48 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Anganawadi building at Flower Garden Main road, Cheluvadipalya, Ward No:138, Bangalore-18 | 19.9 | BBMP | 9.8 | under progress | 10.1
49 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of High Tech Dining Hall and High Tech Library building in Karnataka Pradesh Arya Idigara Sangha -185, Idiga Bhavan 2nd floor RajeevGandhi Circle, Sheshadripuram, Bangalore | 25 | Nirmithi kendra | 25 | completed | 0
50 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of High Tech toilets and bath rooms in Brahmana Vidyarthi Sahaya Sangha Sheshadripuram, Bangalore-20 | 5 | Nirmithi kendra | 2.5 | under progress | 2.5
51 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of borewell -submersible pumpset and overhead tanks and taps at- K.P.Agrahara Ward 9th cross, Bangalore | 5.35 | Nirmithi kendra | 2.7 | under progress | 2.65
52 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of borewell -submersible pumpset and overhead tanks and taps at- 1st cross, M.R.Lane, Cottonpet, Bangalore | 5.35 | Nirmithi kendra | 2.7 | under progress | 2.65
53 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of borewell -submersible pumpset and overhead tanks and taps at- Netajinagar, K.P.Agrahara , Bangalore | 5.35 | Nirmithi kendra | 2.7 | under progress | 2.65
54 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of borewell -submersible pumpset and overhead tanks and taps at-1st main, Magadi road, W.No:120- Bangalore | 5.35 | Nirmithi kendra | 2.7 | under progress | 2.65
55 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of borewell -submersible pumpset and overhead tanks and taps at- 6th cross, Magadi road, W.No:120- Bangalore | 5.35 | Nirmithi kendra | 2.7 | under progress | 2.65
56 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Two Library rooms at Govt. P.u.College Varthuru Mahadevapura Assembly const. | 10 | Nirmithi kendra | 5 | under progress | 5
57 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Supply of Computers and printersd to Nau Bahar Shah School, [Govt. Aided school] No:140, Mackane road, Bharathinagar, Bangalore-1 | 3.044 | Maruthi computers Enterprises | 3.044 | completed | 0
58 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Senior Citizen Bhavana Ward no: 58, New Thippasandra HAL 3rd stage C.V.Raman nagara const.[1st stage] | 10 | EEPRED | 5 | under progress | 5
59 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Senior Citizen Bhavana Ward no: 58, New Thippasandra HAL 3rd stage C.V.Raman nagara const.[2nd stage] | 10 | EEPRED | 5 | under progress | 5
60 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Stri Shakthi Bhavan Ward No: 58, New Thippasandra HAL 3rd stage C.V.Raman Nagar, Const.[Stage-1] | 10 | EEPRED | 0 | under progress | 10
61 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Stri Shakthi Bhavan Ward No: 58, New Thippasandra HAL 3rd stage C.V.Raman Nagar, Const.[Stage-2] | 10 | EEPRED | 0 | under progress | 10
62 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Sanskruthi Bhavan of Kannada Sanskruthi mahila Koota, Ward No: 58, New Thippasandra HAL 3rd stage C.V.Raman Nagar, Const. | 10 | EEPRED | 0 | under progress | 10
63 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of 2 Borewell along with pumpset and PVC pipelines at 1] Govindapura Ward 2] Hennur Garden H.B.R. Layout | 11 | EEPRED | 0 | under progress | 11
64 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Class rooms at B.B.M.P Urdu School Jagjeevanram nagar, Chamarajapet Assembly const. | 2.5 | EEPRED | 1.25 | under progress | 1.25
65 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of office room at B.B.M.p Urdu School J.J.R. Nagar Ward no:137, Chamarajapet Assembly const.-1 | 2.5 | EEPRED | 1.25 | under progress | 1.25
66 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of office room at B.B.M.p Urdu School J.J.R. Nagar Ward no:137, Chamarajapet Assembly const.-2 | 2.5 | EEPRED | 1.25 | under progress | 1.25
67 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Staged Urinals block B.B.M.p Urdu school J.J.R. nagar ward No: 137, Chamarajpet Assembly const. | 2.5 | EEPRED | 1.25 | under progress | 1.25
68 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Additional construction of class rooms at new fort-school and college Pampa mahakavi road, Ward No: 140, Chamarajpet Assembly const. | 2.5 | EEPRED | 0 | under progress | 2.5
69 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of class rooms at new fort college Pampa mahakavi road, Ward No: 140, Chamarajpet Assembly const. | 2.5 | EEPRED | 0 | under progress | 2.5
70 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Library room at new fort-school and college Pampa mahakavi road, Ward No: 140, Chamarajpet Assembly const. | 2.5 | EEPRED | 0 | under progress | 2.5
71 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Laboratory at new fort-school and college Pampa mahakavi road, Ward No: 140, Chamarajpet Assembly const. | 2.5 | EEPRED | 0 | under progress | 2.5
72 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Staff room at new fort-school and college Pampa mahakavi road, Ward No: 140, Chamarajpet Assembly const. | 2.5 | EEPRED | 0 | under progress | 2.5
73 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Rangamantapa katamnallur Mahadevapura Assembly const. | 5 | EEPRED | 0 | under progress | 5
74 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of School compound at Bldave Agrahara Mahadevapura Assembly const. | 5 | EEPRED | 0 | under progress | 5
75 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Ambedkar bhavan Mandura, Mahadevapura Assembly const. | 10 | EEPRED | 0 | under progress | 10
76 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Sri.Samavasha Sahasarjuna Skshathriya Samaja Hostel Sheshadripuram, Banglaore | 15 | EEPRED | 0 | under progress | 15
77 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of School hostel building and Auditorium Kumarakrupa Road, Bangalore | 10 | EEPRED | 0 | under progress | 10
78 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Aduditorium and Hitech library building at no: 19 , Yadava Sangha H>R.B.R Extn, Banasavadi Main Road, Bangalore | 25 | EEPRED | 12.5 | under progress | 12.5
79 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Costruction of Hitech library building bangalore Thamil Sangham Mudaliar road, Shivajinagar, Bangalore | 16.7 | EEPRED | 0 | under progress | 16.7
80 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Govt. Junior Primary Scbhool at ward No: 58 Byrasandra C.V.Raman nagar Ass. Const [Stage-1] | 10 | EEPRED | 0 | under progress | 10
81 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Govt. Junior Primary Scbhool at ward No: 58 Byrasandra C.V.Raman nagar Ass. Const [Stage-2] | 10 | EEPRED | 0 | under progress | 10
82 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of New Kalyani and developmental works at ward No: 80 Maramma devi temple at Hoysalanagar, C.V.Raman nagar Const. Bangalore [Stage-1] | 10 | EEPRED | 10 | completed | 0
83 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of New Kalyani and developmental works at ward No: 80 Maramma devi temple at Hoysalanagar, C.V.Raman nagar Const. Bangalore [Stage-2] | 10 | EEPRED | 10 | completed | 0
84 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of New Kalyani and developmental works at ward No: 80 Maramma devi temple at Hoysalanagar, C.V.Raman nagar Const. Bangalore [Stage-3] | 10 | EEPRED | 10 | completed | 0
85 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of New Kalyani and developmental works at ward No: 80 Maramma devi temple at Hoysalanagar, C.V.Raman nagar Const. Bangalore [Stage-4] | 10 | EEPRED | 10 | completed | 0
86 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Devanga Sangha college building Devaga Hostel road, S.R.Nagar, Bangalore | 15 | Nirmithi kendra | 7.5 | under progress | 7.5
87 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of borewell at venkataram nagar ward no:140, and 141, Valmikinagar Bangalore | 5.35 | EEPRED | 5.35 | completed | 0
88 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Providing submercible pump, panel borard, overhead tank, pipes and taps at venkataram nagar ward no:140, and 141, Valmikinagar Bangalore | 5.35 | EEPRED | 5.35 | completed | 0
89 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps at - Salappa Layout Ward No: 137, Bangalore | 5.35 | EEPRED | 5.35 | completed | 0
90 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps at - Padarayana palya Ward No: 138, Bangalore | 5.35 | EEPRED | 5.35 | completed | 0
91 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps at -Ranasinghpet Ward No: 139, Bangalore | 5.35 | EEPRED | 5.35 | completed | 0
92 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps at -Ramaswamy Palya Ward No: 28, Bangalore | 5.35 | EEPRED | 0 | under progress | 5.35
93 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps at -Subbaiah Palya Ward No: 28, Bangalore | 5.35 | EEPRED | 0 | under progress | 5.35
94 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Providing water tank and pipeline at Sri.Raman Mandira, 4th m-block, 59-c cross, Ward No: 108 Bangalore | 5 | EEPRED | 0 | under progress | 5
95 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of three class rooms at 2nd floor at Govt Urdu Primary and English High School, Bangalore Ward No: 137 | 15.7 | EEPRED | 0 | under progress | 15.7
96 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Auditorium at 3rd floor at Govt Urdu Primary and English High School, Bangalore Ward No: 138 | 12.5 | EEPRED | 0 | under progress | 12.5
97 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps being at Nagavara Govt School Ward No: 24, Sc/ST colony, Bangalore | 5.35 | EEPRED | 0 | under progress | 5.35
98 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of Anganwadi building and computer centre ground floor and first floor at K.G.Halli, wardNo; 30 Bangalore | 17 | EEPRED | 0 | under progress | 17
99 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Construction of hitech library building at ward No; 108, Sri.Vitala Mandira Trust, # 691, 45 cross, 3rd block, Rajajinagar, Bangalore-10 | 10 | EEPRED | 5 | under progress | 5
100 | P.C.Mohan | M.P, Lokasabha | 2011-12 | Civil construction of Dormitary at Bal. Bhavan Premises cubbon park, Bangalore | 25 | EEPRED | 0 | under progress | 25
101 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Construction of rooms in Gandhi vidya school ward No: 97, Dayanandanagar, Srirampura, Bangalore | 20 | EEPRED | 0 | under progress | 20
102 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Construction of 3 class rooms at I.M.N.Govt aided school, ward No: 91, Bangalore | 17 | EEPRED | 0 | under progress | 17
103 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Installing grills to N.B.S. Govt primary and High school, Kackan Road, Ward no: 80, Bangalore | 2 | EEPRED | 0 | under progress | 2
104 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Construction of toilets at ward No: 110, city civil court Shivajinagar, Bangalore | 10 | EEPRED | 0 | under progress | 10
105 | P.C.Mohan | M.P, Lokasabha | 2012-13 | ಆರೋಗ್ಯ ಸಂಕೀರ್ಣ ಮತ್ತು ಯೋಗಾ ಹಾಲ್ ಕಟ್ಟಡ ನಿರ್ಮಾಣಕ್ಕಾಗಿ ವಾರ್ಡ್ ನಂ:85, ದೊಡ್ಡನೆಕ್ಕುಂದಿ ಸಿ.ಎ. ನಿವೇಶನ ನಂ: 8ಪಿ[1] ಎ.ಇ.ಸಿ.ಎಸ್. ಲೇಔಟ್ ಕುಂದಲಹಳ್ಳಿ ಬೆಂಗಳೂರು | 25 | EEPRED | 0 | under progress | 25
106 | P.C.Mohan | M.P, Lokasabha | 2012-13 | ಶಾಲಾ ಕೊಠಡಿಗಳ ನಿರ್ಮಾಣ ಕೆಲಸ ಸಿದ್ದಗಂಗಾ ವಿದ್ಯಾಸಂಸ್ಥೆ, ಶಿವನಗರ ವಾರ್ಡ್ ನಂ: 107, ಬೆಂಗಳೂರು | 5 | EEPRED | 0 | under progress | 5
107 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Construction of Modern Smart class rooms at Terrace area ward No: 49, Dr. Chandrashekar Institute of Speech and hearing Hennur road, Lingarajapuram, Bangalore | 25 | Nirmithi kendra | 12.5 | under progress | 12.5
108 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Drilling of borewell at Christian Crematorium at At Ward no: 141, Azad nagar, Bangalore | 5 | EEPRED | 0 | under progress | 5
109 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Drilling of borewell and construction of water tank at J.J.Nagar, Ward No: 136 Bangalore | 5 | EEPRED | 0 | under progress | 5
110 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Drilling of borewell and construction of water tank at Padarayanapura Ward No: 135 Bangalroe | 5 | EEPRED | 0 | under progress | 5
111 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Dismantalling and construction of class rooms chalavadipalya ward No: 138, govt composite high school Dr. T.C.M. Royan Road, Bangalore | 10 | EEPRED | 0 | under progress | 10
112 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Mini water supply scheme at subash nagar 1st cross, ward No: 195, Gandhi nagar Assembly const. Bangalore [Stage-1] | 4.7 | EEPRED | 0 | under progress | 4.7
113 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Mini water supply scheme at subash nagar 1st cross, ward No: 195, Gandhi nagar Assembly const. Bangalore [Stage-2] | 3 | EEPRED | 0 | under progress | 3
114 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of Borewell, errection of cistern, providing pump motor with electrical facilities and pipe line works at- 6th cross, K.P.Agrahara Magadi Road, Bangalore | 5 | EEPRED | 0 | under progress | 5
115 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of Borewell, errection of cistern, providing pump motor with electrical facilities and pipe line works at- 4th & 5th cross, K.P.Agrahara Magadi Road, Bangalore | 5 | EEPRED | 0 | under progress | 5
116 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of Borewell, errection of cistern, providing pump motor with electrical facilities and pipe line works at- 7th cross, K.P.Agrahara Magadi Road, Bangalore | 5 | EEPRED | 0 | under progress | 5
117 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of Borewell, errection of cistern, providing pump motor with electrical facilities and pipe line works at- 5th and 13th cross, Bhuvaneshwarinagar, Magadi Road, Bangalore | 5 | EEPRED | 0 | under progress | 5
118 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of Borewell, errection of cistern, providing pump motor with electrical facilities and pipe line works at- 15th cross, Bhuvaneshwarinagar, Magadi Road, Bangalore | 5 | EEPRED | 0 | under progress | 5
119 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of Borewell, errection of cistern, providing pump motor with electrical facilities and pipe line works at- 7th cross, A-block, K.P.Agrahara, Magadi Road, Bangalore | 5 | EEPRED | 0 | under progress | 5
120 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of Borewell, errection of cistern, providing pump motor with electrical facilities and pipe line works at- Govt. Kannada and English Primary School, K.P.Agrahara, Magadi Road, Bangalore | 5 | EEPRED | 0 | under progress | 5
121 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of Borewell, errection of cistern, providing pump motor with electrical facilities and pipe line works at- 6th cross, Near Ganesh Temple behind Gopalpura, Magadi Road, Bangalore | 5 | EEPRED | 0 | under progress | 5
122 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of Borewell, errection of cistern, providing pump motor with electrical facilities and pipe line works at- Gopalpura main road, D- cross, Behind Minarva mill, Bangalore | 5 | EEPRED | 0 | under progress | 5
123 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of Borewell, errection of cistern, providing pump motor with electrical facilities and pipe line works at- 2nd cross, New Binny layout, Nagara katte Temple road, Bangalore | 5 | EEPRED | 0 | under progress | 5
124 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of Borewell, errection of cistern, providing pump motor with electrical facilities and pipe line works at- 1st main, near Kalikamba temple, New Binny layout, Bangalore | 5 | EEPRED | 0 | under progress | 5
125 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of Borewell, errection of cistern, providing pump motor with electrical facilities and pipe line works at- No: 415, 1st main, New Binny layout, Bangalore | 5 | EEPRED | 0 | under progress | 5
126 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Improvements to Gymashium building on TCM Royan road in Gandhinagar Assembly const. Bangalore | 2.5 | EEPRED | 0 | under progress | 2.5
127 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of borewell at ward No: 120, K.P.Agrahara Magadi road, Bangalore | 1.8 | EEPRED | 0 | under progress | 1.8
128 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Providing Pumping Machinery for borewell at K.P.Agrahara Magadi road, in Gandhinagar Assembly const. Bangalore | 1.7 | EEPRED | 0 | under progress | 1.7
129 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Providing pipeline for borewell at K.P.Agrahara Magadi road in Gandhinagar Assembly const. Bangalore | 1.5 | EEPRED | 0 | under progress | 1.5
130 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of borewell at M.R.Lane, Cottonpet, Gandhinagar Assembly const. Bangalore | 1.8 | EEPRED | 0 | under progress | 1.8
131 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Providing Pumping Machinery for borewell at M.R.Lane, Cottonpet, Gandhinagar Assembly const. Bangalore | 1.7 | EEPRED | 0 | under progress | 1.7
132 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Providing pipeline for borewell at M.R.Lane, Cottonpet, Gandhinagar Assembly const. Bangalore | 1.5 | EEPRED | 0 | under progress | 1.5
133 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of borewell at Nalbanwadi Cottonpet, Gandhinagar Assembly const. Bangalore | 1.8 | EEPRED | 0 | under progress | 1.8
134 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Providing Pumping Machinery for borewell at Nalbanwadi , Cottonpet, Gandhinagar Assembly const. Bangalore | 1.7 | EEPRED | 0 | under progress | 1.7
135 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Providing pipeline for borewell at Nalbanwadi , Cottonpet, Gandhinagar Assembly const. Bangalore | 1.5 | EEPRED | 0 | under progress | 1.5
136 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Sinking of borewell at N.M.Lane, Cottonpet, Gandhinagar Assembly const. Bangalore | 1.8 | EEPRED | 0 | under progress | 1.8
137 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Providing Pumping Machinery for borewell at N.M.Lane, Cottonpet, Gandhinagar Assembly const. Bangalore | 1.7 | EEPRED | 0 | under progress | 1.7
138 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Providing pipeline for borewell at N.M.Lane, Cottonpet, Gandhinagar Assembly const. Bangalore | 1.5 | EEPRED | 0 | under progress | 1.5
139 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Improvements to Toilets in Labourers Fellowship school No.22 in Gandinagar Assembly Constituency, Bangalore | 2.5 | EEPRED | 0 | under progress | 2.5
140 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Providing Cobble Stones at Play Area in Labourers Fellowship shool No.22 Risaldhar Street, Seshadreipuram, Bangalore in Gandinagar Assembly Constituency, Bangalore Stage-1 | 2.5 | EEPRED | 0 | under progress | 2.5
141 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Providing Cobble Stones at Play Area in Labourers Fellowship shool No.22 Risaldhar Street, Seshadreipuram, Bangalore in Gandinagar Assembly Constituency, Bangalore Stage-2 | 2.5 | EEPRED | 0 | under progress | 2.5
142 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Drilling of Borewell and erection of Cistern with electrification. At Lakshmana Puri, Behind Khodays factory. | 2.5 | EEPRED | 0 | under progress | 2.5
143 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Erection of Submersible pump set with laying pipeline with taps At Lakshmana Puri, Behind Khodays factory. | 2.5 | EEPRED | 0 | under progress | 2.5
144 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Drilling of Borewell and erection of Cistern with electrification. At 2nd Main, 2nd Cross, Near Lakshmana Rao Park, Okalipuram, Bangalore | 2.5 | EEPRED | 0 | under progress | 2.5
145 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Erection of Submersible pump set with laying pipeline with taps At 2nd Main, 2nd Cross, Near Lakshmana Rao Park, Okalipuram, Bangalore. | 2.5 | EEPRED | 0 | under progress | 2.5
146 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Drilling of Borewell and erection of Cistern with electrification. At Near Gandhi Statue, 1st Main, Ramachandrapuram, Bangalroe | 2.5 | EEPRED | 0 | under progress | 2.5
147 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Erection of Submersible pump set with laying pipeline with taps At Near Gandhi Statue, 1st Main, Ramachandrapuram, Bangalroe | 2.5 | EEPRED | 0 | under progress | 2.5
148 | P.C.Mohan | M.P, Lokasabha | 2012-13 | Drilling of Borewell and erection of Cistern with electrification near Draupadamma Temple, V.R. Naidu Nagar, (Swatanthrapalya) Gandhinagar, Bangalore | 2.5 | EEPRED | 0 | under progress | 2.5
149 | P.C.Mohan | M.P, Lokasabha |  | Erection of Submersible pump set with laying pipeline with taps near Draupadamma Temple, V.R. Naidu Nagar, (Swatanthrapalya) Gandhinagar, Bangalore | 2.5 | EEPRED | 0 | under progress | 2.5

## Sheet2 (hidden)
| 10 |  | 9.95 | 0.05
| 10 |  | 9.95 | 0.05 |  | 2.4875 | 2.5125
| 10 |  | 9.95 | 0.05 |  | 10 | 0
| 10 |  | 9.95 | 0.05 |  | 4.75 | 4.75
| 5 |  | 4.975 | 0.025 |  | 25 | 0
| 2.5 |  | 2.4875 | 0.0125 |  | 42.2375 | 7.2625
| 2.5 |  | 2.4875 | 0.0125
| 2.5 |  | 2.4875 | 0.0125
| 2.5 |  | 2.4875 | 0.0125
| 10 |  | 9.95 | 0.05
| 21.5 |  | 21.3925 | 0.1075 |  |  |  | 2.7
| 12 |  | 12 | 0 |  |  |  | 4
| 20 |  | 19.9 | 0.1 |  |  |  | 3
| 5 |  | 4.98 | 0.02 |  |  |  | 3.13
| 5 |  | 4.98 | 0.02
| 128.5 |  | 127.9275 | 0.5725
|  | 2.5 |  |  | 2.5 |  |  | 3.03
|  | 15 |  |  | 15 |  |  | 3
|  | 5 |  |  | 5 |  |  | 2
|  | 10 |  |  | 10 |  |  | 3
|  | 15 |  |  | 15 |  |  | 2.5
|  | 8 |  |  | 8 |  |  | 2.5
|  | 6 |  |  | 6 |  |  | 2.5
|  | 9.6 |  |  | 9.6 |  |  | 50
|  | 7 |  |  | 71.1 |  |  | 20
|  | 3 | [5 empty] | 10
|  | 5 | [5 empty] | 2.7
5
5
5
|  | 5 |  |  |  |  | 5 |  | 5
|  | 6.2 |  |  |  |  | 10 |  | 10
|  | 6.2 |  |  | 5 |  | 10 |  | 3.044
|  | 10 |  |  | 10 |  | 10 |  | 10
|  | 5.4 |  |  | 10 |  | 10 |  | 10
|  | 5 |  |  | 10 |  | 10 |  | 10
|  | 4.3 |  |  | 10 |  | 5 |  | 10
|  | 0.74124 |  |  | 10 |  | 2.5 |  | 10
|  | 143.9412 |  |  | 5 |  | 2.5 |  | 11
5 |  |  |  |  | 2.5 |  | 2.5 |  | 2.5
10 |  |  |  |  | 2.5 |  | 2.5 |  | 2.5
3.044 |  |  |  |  | 2.5 |  | 10 |  | 2.5
10 |  |  |  |  | 2.5 |  | 21.5 |  | 2.5
10 |  |  |  |  | 10 |  | 19 |  | 2.5
10 |  |  |  |  | 80 |  | 120.5 |  | 2.5
10 | [8 empty] | 2.5
10 | [8 empty] | 2.5
11 | [8 empty] | 2.5
2.5 | [8 empty] | 15
2.5 | [8 empty] | 25
2.5 | [8 empty] | 141.5439
2.5
2.5
2.5 | 5
2.5 | 10
2.5 | 3.044
2.5 | 10
15 | 10
25 | 10
16.7 | 10
10 | 10
10 | 11
10 | 2.5
10 | 2.5
10 | 2.5
10 | 2.5
15 | 2.5
5.35 | 2.5
5.35 | 2.5
243.9439 | 2.5
2.5
15
25
16.7
10
10
10
10
10
10
15
5.35
5.35
5.35
5.35
5.35
5.35
5.35
5
15.7
12.5
5.35
17
10
25
361.244

## Sheet1 (hidden)
Administrative sanction accorded but not completed within 90 days and also Estimates are still awaited
Sl No | Name & Location of the work | Estimated Cost [in Lakhs] | Stage of the work | Implementing Agency | Expenditure incurred | Balance if any | Remarks | page No 46
1 | Drilling of 2 Borewell along with pumpset and PVC pipelines at 1] Govindapura Ward 2] Hennur Garden H.B.R. Layout | 11 | Sanction Accorded | EEPRED | 0 | 11 |  | Page No 54
2 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps at -Ramaswamy Palya Ward No: 28, Bangalore | 5.35 | Estimated awaited | EEPRED | 0 | 5.35
3 | Drilling of borewell and providing sumercible pumpset panel road, overhead tank, water poipes with taps at -Subbaiah Palya Ward No: 28, Bangalore | 5.35 | Estimated awaited | EEPRED | 0 | 5.35
4 | Providing water tank and pipeline at Sri.Raman Mandira, 4th m-block, 59-c cross, Ward No: 108 Bangalore | 5 | Estimated awaited | EEPRED | 0 | 5
5 | Construction of three class rooms at 2nd floor at Govt Urdu Primary and English High School, Bangalore Ward No: 137 | 15.7 | Estimated awaited | EEPRED | 0 | 15.7
6 | Construction of Auditorium at 3rd floor at Govt Urdu Primary and English High School, Bangalore Ward No: 138 | 12.5 | Estimated awaited | EEPRED | 0 | 12.5
7 | Civil construction of Dormitary at Bal. Bhavan Premises cubbon park, Bangalore | 25 | Estimated awaited | EEPRED | 0 | 25
8 | Construction of Rangamantapa Kattamanallur Mahadevapura Assembly | 5 | Estimated awaited | EEPRED | 0 | 5
9 | Construction of School Compound at Badavane agrahara Mahadevapura Assembly Contituency | 5 | Estimated awaited | EEPRED | 0 | 5
10 | Construction of Ambedkar Bhavan Mandura Mahadevapura Assembly Constituency | 10 | Estimated awaited | EEPRED | 0 | 10
11 | Construction of School Hostel Building and Auditorium Kumara Krupa Road Bangalore | 10 | Estimated awaited | EEPRED | 0 | 10
12 | Drilling of Borewell and submercible pumpset, pannel board, overhead tank, water pipes with taps | 5.35 | Estimated awaited | EEPRED | 0 | 5.35
1) Ramaswamy Palya Ward No .28
| 2) Subbaiah palya Ward No.28 | 5.35 | Estimated awaited | EEPRED | 0 | 5.35
13 | Construction of water tank and pipeline at Sri.Ramamandira, 4th Block, 59 C cross Ward no.108 | 5 | Estimated awaited | EEPRED | 0 | 5
14 | Construction of 3 class rooms at 2nd floor ward No.137, | 15.7 | Estimated awaited | EEPRED | 0 | 15.7
15 | Construction auditorium at 3rd Floor, at Govt urdu Primary & English High School Ward No.137 | 12.5 | Estimated awaited | EEPRED | 0 | 12.5
16 | ಬಿದರಹಳ್ಳಿ ಗ್ರಾಮ, ಬೆಂಗಳೂರು ಪೂರ್ವ ಬೆಂಗಳೂರು ಇಲ್ಲಿ ಶಾಲಾ ಕೊಠಡಿ ಮತ್ತು ಗ್ರಂಥಾಲಯ ನಿರ್ಮಾಣ ಕಾಮಗಾರಿ | 5 | under progress | EEPRED | 0 | 5 |  | 2012-13

## Sheet3 (hidden)
2.7
4
3.13
3.13
2.7
15.66

## Sheet4 (hidden)
3.03
25
5
3
2
3
2.5
2.5
50
20
100
10
12.5
25
100
20
10
393.53

## 2014-15
Physical & Financial Progress on Implementation of MPLADS works in Bangalore [Urban] District
Name of the M.P. : Sri P.C.Mohan, Hon'ble MP. Lok Sabha
Sl No | Name & Location of the work | Estimated Cost [in Lakhs] | Stage of the work
1 | 2 | 3 | 9
1 | Providing Infrastructure to Gymnasium ward No.136 J J R nagar Azadnagar Chamarajpet Bangalore | 10.11 | Completed
2 | Drilling of Borewell Submermessible pump set Panel Board, Electricification with waterpipes ward No.141 Azadnagar Vittalanagar (SC Colony) 2nd Main Road Bangalore | 2.43 | Completed
3 | Submerssible pumpset panel board electrificationwith waterpipes | 4.05 | Completed
4 | Construction of Senior Citizen Library, Yoga centre Public fecilitation, Ladies Gymnasium & Service Centre ward No.140 Chamarajpet, near venlock Hospital Bangalore Ground Floor | 28.09 | Under Progress
5 | Construction of Senior Citizen Library, Yoga centre Public fecilitation, Ladies Gymnasium & Service Centre ward No.140 Chamarajpet, near venlock Hospital Bangalore First Floor | 20.6 | Under Progress
6 | Providing Infrastructure to Badminton court ward No.140 Chamarajpet Kanniyara Colony Bangalore | 16.75 | Completed
7 | Construction of ITPL Halt station between Krishnarajapuram & Whitefield Railway Stations ward No.54 Hudi. ITPL Bangalore | 99 | Completed
8 | Additional works to Construction of ITPL Halt Station between Krishnarajapuram & White Field Railway Stations Ward No.54, Hudi, ITPL Bangalore | 76 | Completed
9 | Construction of Library Hall on First Floor of an existing Ground Floor Building, ward No.98, Prakash Nagar, Sai College Ground, Beside Vajpayee Building Bangalore | 20 | Completed
10 | Construction of Modren Toilets & Urinals ward no.98 Prakash Nagar, Gayathri Devi Park, Bangalore | 8 | Completed
11 | Construction of New Primary school building ward No.24 Nagawara Bangalore | 15 | Completed
12 | Construction of Two Foot Bridge at Sri.Rama Temple play ground HBR Layout ward No.29, Kacharakanahalli, Bangalore | 8 | Completed
13 | Construction of Auditorium ward No.99, Rajajinagar, Sri Jagajyothi Basaveshwara Sahakara Sangha (Basaveshwara Educational Institutions )2nd Block Rajajinagar Bangalore | 25 | Under Progress
14 | Construction of Auditorium at Jaigopal Garodia Rashtrothana Vidya Kendra Ward No.29 Kacharakanahalli, HRBR Layout, Kalyan Nagar, Bangalore | 25 | Completed
15 | Construction of Rangamandira Building Yarappanahalli Village Bidarahalli Hobli, Kannuru Grama Panchayat, Bangalore East Taluk | 15 | Completed
16 | Construction of Pure Drinking Water Unit & Building Yarappanahalli Colony Yarappanahalli Village, Bidarahalli Hobli, kannuru Grama Panchayat, Bangalore East Taluk | 12 | Completed
17 | Construction of New Agricultural Seva Co operative Society Building Ward No.149, Varthur Bangalore | 0 | Cancelled
18 | Drilling of Borewell and erection of cistren with electrification of ward No.96 1st Main Road, Okalipuram, Bangalore | 2.5 | Completed
19 | Erection of submersible pump set with laying pipeline with taps at ward No.96 1st Main Road, Okalipuram Bangalore | 2.5 | Completed
20 | Drilling of borewell and erection of cistren with electrification of ward No.96 5th Main (Slum) Okalipuram, Bangalore | 2.5 | Completed
21 | Erection of submersible pump set with laying pipeline with taps at ward No.96, 5th Main (Slum) Okalipuram, Bangalore | 2.5 | Completed
22 | Drilling of borewell and erection of cistren with electrification ward No.96, 1st Main road, Brahmapuram, Bangalore | 2.5 | Completed
23 | Erection of submersible pump set with laying pipeline with taps at ward No.96, 1st Main road, Brahmapuram, Bangalore | 2.5 | Completed
24 | Construction of Anganawadi and Library Building ward No.138, Chalavadipalya Anjanappa Garden, 3rd cross, New Layout Bangalore | 22.5 | Completed
25 | Construction of Over Head Tank & all round Pipeline at Yarappanahalli Colony in Yarappanahalli Village | 25 | Completed
26 | Construction of Toilet Block Yarappanahalli Colony, Yarappanahalli Village, Bidarahalli Hobli, Kannuru Grama Panchayat, Bangalore East Taluk | 12 | Completed
27 | Construction of Samudhaya Bhavan Yarapanahalli Village Bidarahalli Hobli, Kannuru Grama Panchayat, Bangalore East Taluk | 24 | Completed
28 | Construction of Computer hall & Bangalore one Building 1st Floor, Ward No.27, Banasawadi, Bangalore Change of Work:- Construction of Computer Hall at Ground Floor ward No.27, Banasawadi, Bangalore | 10 | Completed
| 2% Administrative Charges | 10 | Completed
| ಕಾಮಗಾರಿಗೆ ನೀಡಿರುವ ಒಟ್ಟು ಮೊತ್ತ;- | 503.53 | 29

## 2011-12 under progress (hidden)
Physical & Financial Progress on Implementation of MPLADS works in Bangalore [Urban] District
Name of the M.P. : Sri P.C.Mohan, Hon'ble MP. Lok Sabha | [5 empty] | Year : 2011-12
Sl No | Name & Location of the work | Estimated Cost [in Lakhs] | Stage of the work | Implementing Agency | Expenditure incurred | Balance if any | Remarks
3 | PÉÆqÀw ¥ÀAZÁ¬Äw-PÉÆqÀw PÁ¯ÉÆÃ¤ E°è ¸ÀªÀÄÄzÁAiÀÄ ¨sÀªÀ£À ¤ªÀiÁðt PÁªÀÄUÁj | 10 | under progress | EEPRED | 0 | 10
4 | ªÁqïð £ÀA.112, zÉÆªÀÄä®ÆgÀÄ, ºÉZï.J.J¯ï. 2£ÉÃ ºÀAvÀ, 13£ÉÃ ªÀÄÄRågÀ¸ÉÛ, ºÀwÛgÀ EgÀÄªÀ ¥ÁPïð £À°è fªÀiï PÉÆoÀr ªÀÄvÀÄÛ ±ËZÁ®AiÀÄ ¤ªÀiÁðt ºÁUÀÆ fªÀiï G¥ÀPÀgÀtUÀ¼À£ÀÄß MzÀV¸ÀÄªÀ PÁªÀÄUÁj | 20 | Estimated awaited | EEPRED | 0 | 20
5 | ªÁqïð ¸ÀA.112, zÀÆ¥À£ÀºÀ½î ¨ÉAUÀ¼ÀÆgÀÄ E°è ¥ÁæxÀ«ÄPÀ ±Á¯ÉAiÀÄ zÀÄgÀ¹Ü PÁªÀÄUÁj | 5 | Estimated awaited | EEPRED | 0 | 5
6 | Modernisation and Computerisation of Wxisting Library at Ward No.110, Sampangiram nagar City Civil Court Complex | 25 | Estimated awaited | EEPRED | 0 | 25
|  | 60 |  |  |  | 60

## 2012-13 Under Progress (hidden)
Physical & Financial Progress on Implementation of MPLADS works in Bangalore [Urban] District
Name of the M.P. : Sri P.C.Mohan, Hon'ble MP. Lok Sabha | [5 empty] | Year : 2012-13
Sl No | Name & Location of the work | Estimated Cost [in Lakhs] | Stage of the work | Implementing Agency | Expenditure incurred | Balance if any | Remarks
1 | Sinking of borewell at ward No: 120, K.P.Agrahara Magadi road, Bangalore Providing Pumping Machinery for borewell at K.P.Agrahara Magadi road, in Gandhinagar Assembly const. Bangalore Providing pipeline for borewell at K.P.Agrahara Magadi road in Gandhinagar Assembly const. Bangalore | 5 | Estimate awaited | EEPRED | 0 | 5
2 | Sinking of borewell at M.R.Lane, Cottonpet, Gandhinagar Assembly const. Bangalore Providing Pumping Machinery for borewell at M.R.Lane, Cottonpet, Gandhinagar Assembly const. Bangalore Providing pipeline for borewell at M.R.Lane, Cottonpet, Gandhinagar Assembly const. Bangalore | 5 | Estimate awaited | EEPRED | 0 | 5
3 | Sinking of borewell at Nalbanwadi Cottonpet, Gandhinagar Assembly const. Bangalore Providing Pumping Machinery for borewell at Nalbanwadi , Cottonpet, Gandhinagar Assembly const. Bangalore Providing pipeline for borewell at Nalbanwadi , Cottonpet, Gandhinagar Assembly const. Bangalore | 5 | Estimate awaited | EEPRED | 0 | 5
4 | Sinking of borewell at N.M.Lane, Cottonpet, Gandhinagar Assembly const. Bangalore Providing Pumping Machinery for borewell at N.M.Lane, Cottonpet, Gandhinagar Assembly const. Bangalore Providing pipeline for borewell at N.M.Lane, Cottonpet, Gandhinagar Assembly const. Bangalore | 5 | Estimate awaited | EEPRED | 0 | 5
6 | Construction of School Building SSK Sangha at SSk Primary and Middle School (Govt Sided School ) Somavamsha Saharsa Srjuna Kshtriya (Pattegar) Sangha Regd #2, SSK Bhavan KV Temple Street Balepet Chickpet Ward No.109 Bangalore-560058 | 9.2 | Estimate awaited | Nirmiti kendra | 0 | 9.2
7 | Construction of School Building SSK Sangha at SSK Primary and Middle School (Govt Aided School ) Somavamsha Sahara Arjuna Kshtriya (Pattegar) Sangha Regd #2, SSK Bhavan KV Temple Street Balepet Chickpet ward No.109 Bangalore-560058 | 13 | estimate awaited | Nirmiti kendra | 0 | 13
9 | ªÀÄAqÀÆgÀÄ UÁæªÀÄzÀ ²æÃ.¸ÉÆÃªÉÄÃ±ÀégÀ zÉÃªÀ¸ÁÜ£ÀzÀ PÀ¯ÁåtÂ C©üªÀÈ¢Þ PÁªÀÄUÁj ¨ÉA.¥ÀÆªÀð vÁ®ÆèPÀÄ ©zÀgÀºÀ½î ºÉÆÃ§½ ªÀÄAqÀÆgÀÄ UÁæªÀÄ | 17 | under progress | nirmiti kendra | 8.5 | 8.5
|  | 109.2 | 9 | 9 | 33.5 | 75.7

## 2013-14 Under progress (hidden)
Physical & Financial Progress on Implementation of MPLADS works in Bangalore [Urban] District
Name of the M.P. : Sri P.C.Mohan, Hon'ble MP. Lok Sabha | [5 empty] | Year : 2013-14
| Name & Location of the work | Estimated Cost [in Lakhs] | Stage of the work | Implementing Agency | Expenditure incurred | Balance if any
1 | CAUÀ£ÀªÁr ±Á¯É ºÁUÀÆ MAzÀÄ ¯ÉÊ§æj ¤«Äð¸À®Ä ¨Át¸ÀªÁr ªÁqïð £ÀA.27gÀ ºÀ¼ÉAiÀÄ ¸ÀPÁðj ±Á¯ÉAiÀÄ «¹ÛÃtð 50 x 52 CrUÀ¼À ¸ÀÜ¼ÀzÀ°è | 25 | Estimated awaited | Nirmithi Kendra | 0 | 25
3 | Construction of New Building in Maruthi School Ward No.28, Kammanahalli | 25 | Under Progress | Nirmithi Kendra | 12.5 | 12.5
4 | Supply of Equepments for Mass Casualty care ward No.92, Shivajinagar Bowring & Lady Curzon Hospital near Shivaji nagar Bus stop | 100 | Estimated awaited | Nirmithi Kendra | 0 | 100
5 | ±ËZÁ®AiÀÄ ªÀÄvÀÄÛ ¨sÀzÀævÁ PÉÆoÀrUÉ ²æÃ gÁªÀÄ ªÀÄA¢gÀ ªÁqïð £ÀA.108gÀ §Æån ¸Áàmï GzÁå£ÀªÀ£ÀzÀ°è | 10 | Under Progress | Nirmithi Kendra | 5 | 5
| MlÄÖ | 173 | 6 | 5 | 17.5 | 155.5

## 2015-16
Physical & Financial Progress on Implementation of MPLADS works in Bangalore [Urban] District
Name of the M.P. : Sri P.C.Mohan, Hon'ble MP. Lok Sabha
Sl No | Name & Location of the work | Estimated Cost [in Lakhs] | Stage of the work
1 | 2 | 3 | 9
1 | Construction of Foot Bridge ward No.24 BHR Layout Kacharakanahalli Main Road to Sri Rama Temple Bangalore | 10 | Completed
2 | Syupply of Five Computers with Five Wireless Adapters, Five UPS, Five Computer Table & Chair & One Cisco office Router for Wireless Ward No.91, Bharatinagar BKAM English Higher Primary School, Sangam Road, Bangalore | 2.6 | Completed
3 | Construction of Doddakannalli primary Health Centre Hospital Building Ward No.150 Bellandur, Mahadevapura | 10 | Estimate Pendinge
4 | Drilling of Borewell and erection of cistren with electrification at S.B.Palya, ward No.28, Kammanahalli | 2.5 | Completed
5 | Errection of Submersible pump set with laying pipeline with taps at S.B.Palya, Ward No.28, Kammanahalli | 3 | Completed
6 | Drilling of Borewell and erection of cistren with electrification at KHB Colony, ward No.28, Kammanahalli | 2.5 | Completed
7 | errection of Submersible pump set with laying pipeline with taps at KHB Clolony, ward No.28, Kammanahalli | 3 | Completed
8 | Drilling of Borewell and erection of cistren with electrification at Janakiram Layout, ward No.28 Kammanahalli | 2.5 | Completed
9 | Erection of submersible pump set with laying pipeline with taps at janakiram Layour, ward No.28 Kammanahalli | 3 | Completed
10 | Drilling of borewell and erection of cistren with electrification at Andhra Colony, ward No.28, Kammanahalli | 2.5 | Completed
11 | Erection of submersible pumpset with laying pipeline with taps at Andhra Colony ward No.28, Kammanahalli | 3 | Completed
12 | Drilling of borewell and erection of cistren with electrification at R.S.Palya ward No.28 Kammanahalli | 2.5 | Completed
13 | Erection of submersible pumpset with laying pipeline with taps at R.S.Palya, ward No.28 Kammanahalli | 3 | Completed
14 | Drilling of Borewell and erection of cistren with electrification at Subbannachar Lane, Ward No.120, Cottonpet | 2.5 | Completed
15 | Erection of Submersible pump set with laying pipeline with taps atSubbannachar Lane, Ward No.120, Cottonpet | 3 | Completed
16 | Drilling of Borewell and erection of cistren with electrification at Nagamma Nagar Ward No.120, Cottonpet | 2.5 | Under Progress
17 | Erection of Submersible pump set with laying pipeline with taps at Nagammanagar Ward No.120, Cottonpet | 3 | Under Progress
18 | Drilling of Borewell and erection of cistren with electrification at K.P.Agrahara, 8th Cross, Ward No.120, Cottonpet | 2.5 | Under Progress
19 | Erection of Submersible pump set with laying pipeline with taps at K.P.Agrahara, 8th Cross, Ward No.120, Cottonpet | 3 | Under Progress
20 | Construction of Anganavadi Building at First Floor ward office, Ward No.96, Okalipuram, Bangalore | 0 | Cancelled
21 | Construction of Anganavadi School Building at First Floor Ramachandrapuram Ward No.96, Okalipuram, Bangalore | 0 | Cancelled
22 | Construction of Anganawadi building at Ground Floor at Ward No.27, Banasawadi | 25 | Completed
23 | Development works at Lakshman Rao Park Ward No.96, Okalipuram Bangalore | 11.5 | Completed
24 | 1) Construction of Badminton Court ward No.27, OMBR Layour Banasavadi Stage -1 2, 3, 4, 5, 6, 7, 2) Construction of Badmintion Court Ward No.27, OMBR Layout, Banasavadi | 68.85 | Under Progress
25 | Development of Yoga Center near Gundappa Park ward No.89. Jogupalya Bangalore | 20 | Completed
26 | Providing of Ten (10) numbers of Stainless steel four seater tandem chairs on the platforms at Krantivira Sangolli Rayanna Bangalore city Railway Station Ward No.94, Gandhinagar, Bangalore | 2.5 | Completed
27 | Construction of Foot Over Bridge at ITPL Halt Station between Krishnarajapuram & Whitefield Railway Stations ward No.54, Hudi, ITPL Bangalore | 111.3525 | Under Progress
28 | Construction of Building at Karnataka Welfare Assan for the Blind (NGO) # 69, 1st Main, Nehru Nagar, SC Road, Sheshadripuram, Ward No.94, Gandhinagar, Bangalore | 10 | Under Progress
29 | Construction of Hostel Building at Karnataka Arya Vysya Mahasabha # 16, Sheshadri Road, Gandhinagar Ward No.94, Gandhinagar, Bangalore | 25 | Estimate Pendinge
30 | Development of Park at 3rd Cross Vasantgbagar Ward Bi,93, Vasabthnagar Bangalore | 18 | Completed
31 | Installation of water plant at ward No.138 Chalavadipalya Bangalore | 15 | Estimate Pendinge
32 | Construction of Anganawadi and Library Building at ward No.138 Chalavadipalya Siddarthanagar, Bangalore | 27.91 | Completed
33 | Construction of Building at Karnataka Sengundhar Sangam # 126, 1st Main, 2nd Stage, Okalipuram, Ward No.96, Bangalore | 10 | Completed | 27.91
34 | Modernization of Class Rooms & Installation of Computers at S.N.Vidya Mandir School # 384, 8th Cross, Ambedkarnagar, Near Whitefield Ward No.83, Kadugodi Bangalore | 15 | Estimate Pendinge
35 | Renovation of School Building at Government Higher Primary School, Sindhi, M.B.T.Street, Nagarthpet, Ward No.109, Chickpet, Bangalore | 0 | Cancelled
36 | Construction of Anganawadi building at Saneguravanahalli, Rajajinagar Assembly Constituency, Bangaloe South (Ground Floor & First Floor) | 25 | Completed
37 | Construction of General and Multispeciality hospital of Sri.Krishna Sevashrama Trust Old Airport-Whitefield Road, Marathalli | 25 | Estimate Pendinge
38 | Installation of RO Water plant Narashimaiah Compound, Ward No.137, Rayapuram | 7.63 | Estimate Pendinge
| 2% Administrative Charges | 10 | Under Progress
| ಕಾಮಗಾರಿಗೆ ನೀಡಿರುವ ಒಟ್ಟು ಮೊತ್ತ;- | 494.3425 | 39

## 2016-17
Physical & Financial Progress on Implementation of MPLADS works in Bangalore [Urban] District
Name of the M.P. : Sri P.C.Mohan, Hon'ble MP. Lok Sabha
Sl No | Name & Location of the work | Estimated Cost [in Lakhs] | Stage of the work
1 | 2 | 3 | 9
1 | Modernisation & Computerisation of Existing Library Ward No.110, Sampangiramanagara City Civil Court Complex Change of Work:- Construction of Computer Lab at Existing Library Building, Ward No.110, Sampangiramanagara City Civil Court Complex. | 24 | Under Progress
2 | Construction of RO waterplant with Civil & Fabrication Structure ward No.63, Jayamahal C.No 4th Street Milkman Colony Shivaji Road Cross, Shivajinagar | 10 | Under Progress
3 | Construction of RO waterplant with Civil & Fabrication Structure ward No.62, Ramaswamypalya Gangabadavane, Nandi Durga Road, Shivajinagar | 10 | Under Progress
4 | Contruction of Anganawadi School Building at First Floor Ramachandrapuram ward No.96 Okalipuram Bangalore | 20 | Under Progress
5 | Construction of Anganawadi Building at First Floor ward Office ward No.96, Okalipuram Bangalore | 20 | Under Progress
6 | Drilling of Borewell and erection of cistred with electtrification & Erection of Submersible pump set with laying pipeline with taps ward No.96, 2nd Cross Road, Robertson Block, Okalipuram Bangalore | 5 | Completed
7 | Drilling of Borewell and erection of cistred with electtrification & Erection of Submersible pump set with laying pipeline with taps ward No.96, 2nd Main Road,3rd Cross Road, Ramachandrapuram, Bangalore | 5 | Completed
8 | Drilling of Borewell and erection of cistred with electtrification & Erection of Submersible pump set with laying pipeline with taps ward No.96, , 1st Cross Road, New Kallappa Block, Okalipuram, Bangalore | 5 | Completed
9 | Construction of Samudaya Bhavana Maragondanahalli Village, Bidarahalli Hobli, Bangalore East Taluk Mahadevapura ರದ್ದುಪಡಿಸಲಾಗಿದೆ | 15 | Estimate pending
10 | Supplying of 15 Computers to Govt Primary School Doddabanahalli Village and Grama Panchayathi, Bangalore East Taluk Mahadevapura | 6 | Completed
11 | Construction of Class Room at 1st Floor at Govt Higher Primary School Maragondanahalli Village, Bidarahalli Hobli, Bangalore East Taluk, Mahadevapura ರದ್ದುಪಡಿಸಲಾಗಿದೆ | 5 | Estimate pending
12 | Construction of Compound wall at Govt High School Bidarahalli Hobli, Bangalore East Taluk, Mahadevapura | 15 | Estimate pending
13 | Construction of Gymnasium School Building 1st Floor Kannamangala Village and Panchayati, Bangalore East Taluk Mahadevapura | 9 | Estimate pending
14 | Construction of Shantigiri Ashram's Global Cultural Center Building at Kodathi Villager, Varthur Hobli Bangalore East Taluk Mahadevapura | 25 | 15.06.2018
15 | Providing RO Water Plant at Hallehalli Village, Kithaganur Grama Panchayat, Bidarahalli Hobli, Bangalore East Taluk | 8 | Estimate pending
16 | Construction of Primary Health Centre Building Bidarahalli Hobli, Kannur Grama Panchayat Bangalore East Taluk, Mahadevapura Change of Work:- Construction of Primary Health Centre Building at Doddagubbi Village, Bidarahalli Hobli, Kannur Grama Panchayat, Bangalore East Taluk Mahadevapura | 20 | Estimate pending
17 | ಬೆಂಗಳೂರು ನಗರ ಜಿಲ್ಲೆ, ಚಾಮರಾಜಪೇಟೆ ವಿಧಾನಸಭಾ ಕ್ಷೇತ್ರದಲ್ಲಿನ ಆಜಾದ್ ನಗರ ವಾರ್ಡ್ ನಂ.141 ರಲ್ಲಿನ ಕಣಿಯಾರ್ ಕಾಲೋನಿಯಲ್ಲಿರುವ ಬ್ಯಾಡ್ಮಿಂಟನ್ ಕೋರ್ಟ್ ದುಸ್ಥಿತಿಯಲ್ಲಿದ್ದು ಸದರಿ ಒಂದು ಕೋರ್ಟ್ ಗೆ ವುಡ್ಡನ್ ಫ್ಲೋರಿಂಗ್ ಅಗತ್ಯವಿದ್ದು ಇತರೆ ಅಭಿವೃದ್ದಿ ಕಾಮಗಾರಿ | 10.33 | Under Progress
18 | Construction of Badminton Court at BBMP play ground opposite BDA Complex Austin Town ward No.115, Vannarpet, Bangalore | 70 | Under Progress
19 | Construction of Installation RO Water Purifying Unit BDA Flats, Sustin Town, Ward No.115, Vannarpet, Bangalore | 10 | Estimate pending
20 | Drilling of Borewell and erection of cistern with electrification Dhobighat ward No.30, Kadugondanahalli | 2.5 | Under Progress
21 | Erection of submersible pump set with laying pipeline with taps Dhobighat ward No.30, Kadugondanahalli | 3 | Under Progress
22 | Construction of New Building for Government Model Kannada Higher Primary & High School at Lingarajapuram Ward No.49, Bangalore | 25 | Under Progress
23 | Construction and Installation RO water Puriflying unit with Drilling of borewell and erection of cistern with electrification, Erection of submersible pump set with laying pipeline with taps Ramachandrapuram 3rd Main Road, Ward No.96, Okalipuram Bangalore | 0 | Cancelled
24 | Construction and Installation RO water Puriflying unit with Drilling of borewell and erection of cistern with electrification, Erection of submersible pump set with laying pipeline with taps Gopalapura main Road, Ward No.96, Okalipuram, Bangalore | 0 | Cancelled
25 | Construction of Toilet with Borewell at ITPL halt Station between Krishnarajapuram & Whitefield Railway Stations Ward No.54, Hudi, ITPL Bangalore | 15 | Estimate pending
26 | Construction of Hostel Building (2nd Floor) Sri Somavamsha Sahasrarjuna kshatriya samaj ® # 9, South Central road, Siruru park Road, Seshadripuram, Bangalore | 25 | Estimate pending
27 | Installation of CC TV camera mahadevapura assembly Constituency | 30 | Estimate pending
28 | Construction of Anganawadi Building & Gym Center at IPD Salappa Layout, Ward No.137 Rayapuram | 30 | Estimate pending
29 | Construction of Stage and Providing Sheet Roof work at PVP School K.H.B Colony, Ward No.101, Kamakshipalya | 20 | Estimate pending
30 | Drilling of Borewell and Erection of cistern with electrification, Erection of submersible pupm set with laying pipeline with taps, Ramachandrapuram 3rd Main Road, ward No.96, Okalipuram, Bangalore | 6 | Completed
31 | Construction & Installation of RO Water Purivying Unit Ramachandrapuram 3rd Main Road, Ward No.96, Okalipuram Bangalore | 9 | Under Progress
32 | Drilling of Borewell and erection of cistern with electrification, Erection of submersible pupm set with laying pipeline with taps, Gopalapura Main Road, ward No.96, Okalipuram, Bangalore | 6 | Completed
33 | Construction & Installation of RO Water Purivying Unit Gopalapura Main Road, Ward No.96, Okalipuram Bangalore | 9 | Under Progress
34 | Construction of Student Hostel Thogata Veera Kshatriya Sangha #22/1 Raja Ram Mohan Roy Road, Ward No.110, Sampangiram Nagar, Bangalore | 15.75 | Estimate pending
| 2% Administrative Charges | 10 | Under Progress
| MlÄÖ | 498.58 | 35

## 2017-18
Physical & Financial Progress on Implementation of MPLADS works in Bangalore [Urban] District
Name of the M.P. : Sri P.C.Mohan, Hon'ble MP. Lok Sabha
Sl No | Name & Location of the work | Estimated Cost [in Lakhs] | Stage of the work
1 | 2 | 3 | 9
1 | Construction works at Banjara Bhavan, # 16-K, Miller road, Vasanthnagar, Ward No.93, Bangalore | 20 | Under Progress
2 | Supply of Following medical Equipments to Victoria Hospital, Ward No.139, K.R.Market 1) ABG Machine Radiometer 2) ECG machine 12 Channel 3) Hematology Analyzer Radiometer Fully Automated 4) Unnybiassat Abaktzer Raduineter Fully Automated 5) Portable Ventilators 6) Biochemistry analyzer adiometer Fully Automated 7) Dialysis machine 8) R.O Plant with Ports 100 LPH (Dialysis) 9) Bipap Machines 10) Infusion Pumps B Braum | 103 | Estimate Pendinge
3 | Supply of Following medical Equipments toPediatric and neonatal intensive Care units in Vani Vilas Hospital Ward No.139, K.R.Market 1) Ventilator for PICU & NICU 2) Monitors for PICU & NICU | 117.73 | Completed
4 | Construction & Installation of RO Water Purifying Unit beside Adiministrative offie Premises in Vani Vilas Hospital Ward No.139, K.R.Market | 9 | Estimate Pendinge
5 | Construction of New Shelter Block Infront of Highrisk Pregnancy Premises in Vani Vilas Hospital Ward No.139, K.R.Market | 50 | Estimate Pendinge
6 | Construction o& Installation of RO Water Purifying Unit Infront of Hifhrisk Pregnancy Premises in Vani Vilas Hospital Ward No.139, K.R.Market | 7 | Estimate Pendinge
7 | Construction of New Toilet Block Infront of Highrisk Pregnancy Premises in Vani Vilas Hospital Ward No.139, K.R.Market | 10 | Estimate Pendinge
8 | Construction of New Toiler Block beside Administrative office Premises in Vani Vilas Hospital Ward No.139, K.R.Market | 8 | Estimate Pendinge
9 | Construction of New Shelter Block beside Administrative office Premises in Vani Vilas Hospital Ward No.139, K.R.Market | 13.5 | Estimate Pendinge
10 | Installation of RO Water Purifying Unit along with necessary Accessories 4th Block, Sadbhavana Circle Ward No 108, Sri Rama madira Rajajinagar Assembly | 18.5 | Under Progress
11 | Installation of RO Water Purifying Unit along with necessary Accessories ward No.100 Basaveshwaranagara, Rajajinagar Assembly | 18.5 | Under Progress
12 | Installation of RO Water Purification Unit Vartur (Near Indira Canteen) | 4 | Under Progress
13 | Installation of RO Water Purifying Unit Chikkanayakanahalli mahadevapura | 4 | Under Progress
14 | Installation of RO Water Purifying Unit Byrati Mahadevapura | 4 | Under Progress
15 | Installation of RO Water Purifying Unit Bellishivalaya Mahadevapura | 4 | Under Progress
16 | Installation of RO Water Purifying Unit Kithaganur Colony Mahadevapura | 4 | Under Progress
17 | Installation of RO Water Purifying Unit Vartur (Near Varthur Tank) | 4 | Under Progress
18 | Installation of RO water Ourifier Plant Ward No.138, Chalavadipalya Behind Vinayaka Theatre Bangalore | 9.75 | Estimate Pendinge
19 | Installation of RO water Ourifier Plant Ward No.138, Ittige Anjanappa Garden, Bangalore | 9.75 | Estimate Pendinge
20 | Construction of New Toilet Blocks at Cubbon Park Ward No.110, Sampangiramanagara Bangalore | 20 | Estimate Pendinge
| 2% Administrative Charges | 10 | Under Progress
|  | 448.73 | 21
438.73

## Cheque Issued Details (hidden)
As on
Sl No | Cheque No | Date | Implementing Agency
1 | 226381 | 22.10.2016 | EE RDWS&S | 12 | Clear
2 | 226382 | 22.10.2016 | EE RDWS&S | 25 | Clear
3 | 226383 | 14.11.2016 | EE RDWS&S | 12 | Clear
4 | 226384 | 28.11.2016 | 2% ADM | 15 | Clear
5 | 226385 | 04.01.2017 | EE RDWS&S | 5 | Clear
6 | 226386 | 04.01.2017 | EE RDWS&S | 7.5 | Clear
7 | 226387 | 07.02.2017 | EE RDWS&S | 6 | Clear
8 | 226388 | 07.02.2017 | EE RDWS&S | 9 | Clear
9 | 226389 | Cancelled |  | 0 | Cancelled
10 | 226390 | 14.02.2017 | EE PRED | 15 | Clear
11 | 226391 | 23.02.2017 | Nirmithi Kendra | 21 | Clear
12 | 226392 | 28.02.2017 | South Westren Railway | 83 | Clear
13 | 226393 | 07.03.2017 | KRIDL BBMP | 18 | Clear
14 | 226394 | Cancelled |  | 0 | Cancelled
15 | 226395 | Cancelled |  | 0 | Cancelled
16 | 226396 | 22.03.2017 | Nirmithi Kendra | 25 | Clear | p | as on 12.10.2017 | 56.5
17 | 226397 | 27.04.2017 | Nirmithi Kendra | 51.63 | Clear | P | Cheque Issued | 0
18 | 226398 | 27.04.2017 | Nirmithi Kendra | 15 | Clear | P | Available Balance | 56.5
19 | 226399 | 27.04.2017 | Nirmithi Kendra | 15 | Clear | P
20 | 226400 | 27.04.2017 | Nirmithi Kendra | 15 | Clear
21 | 376701 | 06.06.2017 | EE PRED | 12 | Clear
22 | 376702 | 08.06.2017 | EE PRED | 5 | Clear
23 | 376703 | 08.06.2017 | EE PRED | 5 | Clear
24 | 376704 | 08.06.2017 | EE PRED | 5 | Clear
25 | 376705 | 23.06.2017 | MK Enterprises | 6 | Clear | 10/16-17
26 | 376706 | 23.06.2017 | Railway | 2.5 | Clear | 12/15-16
27 | 376707 | 13.09.2017 | EE PRED | 12 | Clear | 19/14-15
28 | 376708 | 24.10.2017 | Nirmithi Kendra | 8.75 | Clear | 5/14-15
29 | 376709 | 24.10.2017 | EE PRED | 25 | Clear | 8/2015-16
30 | 376710 | 24.10.2017 | Nirmithi Kendra | 7.5 | Clear | 17/16-17
31 | 376711 | 08.11.2017 | EE PRED | 10 |  | 20/14-15
32 | 376712
33 | 376713
34 | 376714
35 | 376715
36 | 376716
37 | 376717
38 | 376718
376719
39 | 376720 |  |  | 448.88
|  |  | Balance | 196

## Sheet6 (hidden)
ಶ್ರೀ.ಪಿ.ಸಿ.ಮೋಹನ್, ಮಾನ್ಯ ಲೋಕಸಭಾ ಸದಸ್ಯರು, ರವರು ಆದರ್ಶ ಗ್ರಾಮ ಯೋಜನೆಯಡಿಯಲ್ಲಿ ರಾಗಿಹಳ್ಳಿ ಗ್ರಾಮವನ್ನು ದತ್ತು ಪಡೆದಿದ್ದು ಈ ಕೆಳಕಂಡಂತೆ ಕಾಮಗಾರಿಗಳನ್ನು ಅನುಷ್ಟಾನಗೊಳಿಸಲು ಕೋರಿರುತ್ತಾರೆ
1 | Construction of Rangamandira Building Yarappanahalli Village Bidarahalli Hobli, Kannuru Grama Panchayat, Bangalore East Taluk | 15 | Completed | 05.11.2015 | 226390 | 14.02.2017
2 | Construction of Pure Drinking Water Unit & Building Yarappanahalli Colony Yarappanahalli Village, Bidarahalli Hobli, kannuru Grama Panchayat, Bangalore East Taluk | 12 | Completed | 23.11.2015 | 226381 | 22.10.2016
3 | Construction of Over Head Tank & all round Pipeline at Yarappanahalli Colony in Yarappanahalli Village | 25 | Completed | 02.01.2016 | 226382 | 22.10.2016
4 | Construction of Toilet Block Yarappanahalli Colony, Yarappanahalli Village, Bidarahalli Hobli, Kannuru Grama Panchayat, Bangalore East Taluk | 12 | Completed | 17.03.2016 | 226383 | 14.11.2016
5 | Construction of Samudhaya Bhavan Yarapanahalli Village Bidarahalli Hobli, Kannuru Grama Panchayat, Bangalore East Taluk | 24 | Under Progress
| ಒಟ್ಟು | 88

## Sheet7 (hidden)
1 | Construction of Karnataka Chitrakala parishath building at Kumara park East, Bangalore | 5 | completed | EEPRED | 5
2 | Construction of Samaloch Bhavan at Karnataka Chitrakala Parishath campus Kumarakrupa road, Bangalore | 10 | completed | EEPRED | 10
3 | Construction of Samudhaya Bhavan at Karnataka Chitrakala Parishath compound, Kumarakrupa Road, Bangalore-01 | 10 | completed | EEPRED | 10
[6 empty] | 309.85 | 199.47

## Sheet5 (hidden)
50370
6697
57067
219208
163434
61031 | 443673
500740

## 2013-14 (hidden)
Physical & Financial Progress on Implementation of MPLADS works in Bangalore [Urban] District
Name of the M.P. : Sri P.C.Mohan, Hon'ble MP. Lok Sabha | [5 empty] | Year : 2013-14
| Name & Location of the work | Estimated Cost [in Lakhs] | Stage of the work | Implementing Agency | Expenditure incurred | Balance if any | SC/ST | File No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | ªÀÄPÀÌ¼À DlzÀ ªÉÄÊzÁ£À DlzÀ ¥ÀjPÀgÀUÀ¼ÀÄ ZÉÊ£ï°APï ¥É¤ßAUï ªÀÄvÀÄÛ C©üªÀÈ¢Þ PÁAiÀÄðUÀ¼ÀÄ ªÀiÁgÀÄw ¸ÉÃªÁ£ÀUÀgÀ ªÁqïð £ÀA.59gÀ ºÉÊ¸ÉÖçÃmï ¥ÁPïð | 3.03 | Completed | Nirmithi Kendra | 3.03 | 0
2 | CAUÀ£ÀªÁr ±Á¯É ºÁUÀÆ MAzÀÄ ¯ÉÊ§æj ¤«Äð¸À®Ä ¨Át¸ÀªÁr ªÁqïð £ÀA.27gÀ ºÀ¼ÉAiÀÄ ¸ÀPÁðj ±Á¯ÉAiÀÄ «¹ÛÃtð 50 x 52 CrUÀ¼À ¸ÀÜ¼ÀzÀ°è | 25 | Estimated awaited | Nirmithi Kendra | 0 | 25 | SC
3 | ªÀÁåAiÀiÁªÀÄ ±Á¯É ¤«Äð¸À®Ä ªÀiÁgÀÄw ¸ÉÃªÁ£ÀUÀgÀ ªÁqïð £ÀA.59gÀ ¸ÀvÁå£ÀUÀgÀzÀ°è | 5 | Completed | EEPRED | 5 | 0
4 | zÉÃªÁAUÀ ¸ÀAWÀ ±Á¯ÉUÉ PÀA¥ÀÆålgï-5 ¦æAlgï-1 ºÁUÀÆ AiÀÄÄ¦J¸ï-1 ¸ÀgÀ§gÁdÄ ªÀiÁqÀ®Ä ²ªÁf£ÀUÀgÀ «zsÁ£À¸À¨sÁ PÉëÃvÀæ ¸ÀA¥ÀAVgÁªÀÄ£ÀUÀgÀ ªÁqïð £ÀA.110 zÉÃªÁAUÀ ¸ÀAWÀ ±Á¯É | 2.7 | Completed | M/s Emerge Technologies | 2.7 | 0
5 | eÉÆåÃw¥ÀÄgÀ UÁæªÀÄzÀ°è ¸ÀPÁðj ±Á¯ÉUÉ PÀA¥ÀÆålgï-8 ¦æAlgï-1 ºÁUÀÆ AiÀÄÄ¦J¸ï-1 ¸ÀgÀ§gÁdÄ ªÀiÁqÀ®Ä ¨ÉA.¥ÀÆªÀð vÁ®ÆèPÀÄ ©zÀgÀºÀ½î ºÉÆÃ§½ ªÀÄAqÀÆgÀÄ UÁæªÀÄ ¥ÀAZÁ¬Äw ªÁå¦ÛAiÀÄ eÉÆÃw¥ÀÄgÀ UÁæªÀÄ | 4 | Completed | M/s Emerge Technologies | 4 | 0 | SC
6 | QvÀÛUÀ£ÀÆgÀÄ UÁæªÀÄzÀ°è ¸ÀPÁðj ±Á¯ÉUÉ PÀA¥ÀÆålgï-6, ¦æAlgï-1 ºÁUÀÆ AiÀÄÄ¦J¸ï-1, ¸ÀgÀ§gÁdÄ ªÀiÁqÀ®Ä ¨ÉA¥ÀÆ.vÁ ©zÀgÀºÀ½î ºÉÆÃ§½ ªÀÄAqÀÆgÀÄ UÁæªÀÄ ¥ÀAZÁ¬Äw ªÁå¦ÛAiÀÄ QvÀÛUÀ£ÀÆgÀÄ UÁæªÀÄ | 3.13 | Completed | M/s Emerge Technologies | 3.13 | 0 | SC
7 | ªÀÄAqÀÆgÀÄ UÁæªÀÄzÀ°è ¸ÀPÁðj ±Á¯ÉUÉ PÀA¥ÀÆålgï-6, ¦æAlgï-1 ºÁUÀÆ AiÀÄÄ¦J¸ï-1, ¸ÀgÀ§gÁdÄ ªÀiÁqÀ®Ä ¨ÉA¥ÀÆ.vÁ ©zÀgÀºÀ½î ºÉÆÃ§½ ªÀÄAqÀÆgÀÄ UÁæªÀÄ ¥ÀAZÁ¬Äw ªÁå¦ÛAiÀÄ ªÀÄAqÀÆgÀÄ UÁæªÀÄ | 3.13 | Completed | M/s Emerge Technologies | 3.13 | 0 | SC
8 | 2 PÉÆ¼ÀªÉ ¨Á«UÀ¼À£ÀÄß PÉÆgÉAiÀÄ®Ä mÁåAPï ¤ªÀiÁðt ¥ÉÊ¥ï ªÀÄvÀÄÛ ¥ÀA¥ÀÄ ªÉÆÃmÁgï C¼ÀªÀr¸À®Ä, gÁeÁf£ÀUÀgÀ «zsÁ£À ¸À¨sÁ PÉëÃvÀæzÀ ²ªÀ£ÀUÀgÀ ªÁqïð £ÀA.107 | 9.6 | Completed | EEPRED | 9.6 | 0
9 | 2 PÉÆ¼ÀªÉ ¨Á«UÀ¼À£ÀÄß PÉÆgÉAiÀÄ®Ä mÁåAPï ¤ªÀiÁðt ¥ÉÊ¥ï ªÀÄvÀÄÛ ¥ÀA¥ÀÄ ªÉÆÃmÁgï C¼ÀªÀr¸À®Ä, ZÁªÀÄgÁd¥ÉÃmÉ «zsÁ£À ¸À¨sÁ PÉëÃvÀæzÀ ZÀ®ÄªÁ¢ ¥Á¼Àå ªÁqïð £ÀA.138, | 9.6 | Completed | EEPRED | 9.6 | 0
10 | Additional works to Construction of New Building ward No 108, Bhuvaneshwari Kannada Yuvakara Gudisalu Nivasigala Sangha 5th Block, Rajajinagara Bangalore-10 | 3 | Completed | Nirmithi Kendra | 3 | 0 |  | File No.12A
11 | ªÀÄPÀÌ¼À PÀÆl GzÁå£ÀªÀ£ÀzÀ°è ªÁåAiÀiÁªÀÄ ¸ÁªÀÄVæUÀ¼À£ÀÄß ¸ÀgÀ§gÁdÄ ªÀiÁqÀ®Ä ZÁªÀÄgÁd¥ÉÃmÉ ªÁqïð £ÀA.140, ZÁªÀÄgÁd¥ÉÃmÉ | 2 | Completed | Nirmithi Kendra | 2 | 0
12 | ªÀÄPÀÌ¼À PÀÆl GzÁå£ÀªÀ£ÀzÀ°è ¸ÁªÀðd¤PÀ ±ËZÁ®AiÀÄ ¤«Äð¸À®Ä ZÁªÀÄgÁd¥ÉÃmÉ ªÁqïð £ÀA.140 ZÁªÀÄgÁd¥ÉÃmÉ | 3 | Completed | Nirmithi Kendra | 3 | 0
13 | DeÁzï £ÀUÀgÀ GzÁå£ÀªÀ£ÀzÀ°è ¸ÁªÀðd¤PÀ ±ËZÁ®AiÀÄ ¤«Äð¸À®Ä ZÁªÀÄgÁd¥ÉÃmÉ ªÁqïð £ÀA.140 DeÁzï £ÀUÀgÀ | 2.5 | Completed | Nirmithi Kendra | 2.5 | 0
14 | £ÀAeÁA§ CUÀæºÁgÀzÀ°è ¸ÁªÀðd¤PÀ ±ËZÁ®AiÀÄ ¤«Äð¸À®Ä ZÁªÀÄgÁd¥ÉÃmÉ ªÁqïð £ÀA.140 £ÀAeÁA§ CUÀæºÁgÀ | 2.5 | Completed | Nirmithi Kendra | 2.5 | 0
15 | Additional works to Construction of Toilets in Civil Court premises ward No.110, Sampangiramanagara city Civil Court Premises | 2.5 | Completed | EEPRED | 2.5 | 0
16 | qÉ¸ïÌ ¸Àè¨ï gÀ¸ÉÛ C¼ÀªÀr¸ÀÄªÀ PÀÄjvÀÄ:- ¸ÀªÀðdÕ£ÀUÀgÀ ªÁqïð £ÀA.79 PÉÆªÀÄ¯ï ºÉÆÃmÉ¯ï ªÀÄÄA¨sÁUÀzÀ°è ªÀÄÄRågÀ¸ÉÛ PÀPïìmË£ï | 50 | Completed | EEPRED | 50 | 0
17 | Construction of Library and Auditorium at ward No.141 Azad nagar Govt urdu Higher primary School | 20 | Completed | EEPRED | 20 | 0
18 | PÉgÉAiÀÄ ¥ÁzÁZÁj ªÀiÁUÀð gÀ¸ÉÛAiÀÄ£ÀÄß C©üªÀÈ¢Þ ¥Àr¸ÀÄªÀ PÀÄjvÀÄ | 100 | Completed | EEPRED | 100 | 0
19 | Supply of 5 Computers with 1 Printer and 1 UPS | 2.7 | Completed | M/s Emerge Technologies | 2.7 | 0
20 | GavÀ «zÁåyð ªÀ¸Àw ¤®AiÀÄ PÀlÖqÀPÉÌ UÁA¢ü£ÀUÀgÀ ªÁ.£ÀA.-94, PÀ£ÁðlPÀ gÁdå ªÀÄrªÁ¼ÀgÀ ¸ÀAWÀ(j) £ÀA.7 ¹gÀÆgÀÄ ¥ÁPïð gÀ¸ÉÛ ±ÉÃµÁ¢æ¥ÀÄgÀA | 10 | Completed | EEPRED | 10 | 0
21 | Construction of Community Hall at Chavatapalem Village, Venkatachalam mandal, Sri.Potti Sriramulu nellore District-524320 Andhra Pradesh | 10 | Completed | Nellur District Andra Pradesh | 10 | 0 |  |  | §zÀ° PÁªÀÄUÁj
22 | ºÁ° EgÀÄªÀ ±ËZÁ®AiÀÄzÀ ªÉÆzÀ®£É ªÀÄºÀr ¤ªÀiÁðt ªÁqïð £ÀA.110, ¸ÀA¥ÀAVgÁªÀÄ£ÀUÀgÀ | 10 | Completed | EEPRED | 10 | 0
23 | ºÀ¼ÉÃ ±ËZÁ®AiÀÄ zÀÄgÀ¹Û PÁªÀÄUÁj ªÀÄvÀÄÛ | 2.5 | Completed | EEPRED | 2.5 | 0
24 | Construction of New Building in Maruthi School Ward No.28, Kammanahalli | 25 | Completed | Nirmithi Kendra | 25 | 0
25 | Supply of Equepments for Mass Casualty care ward No.92, Shivajinagar Bowring & Lady Curzon Hospital near Shivaji nagar Bus stop | 100 | Estimated awaited | Nirmithi Kendra | 0 | 100
26 | ¸À¨sÁAUÀtÀ ºÁUÀÆ UÀæAxÁ®AiÀÄ PÉÆoÀr PÀlÖqÀUÀ¼À ¤ªÀiÁðt PÀAzÁAiÀÄ E¯ÁSÉAiÀÄ £ËPÀgÀgÀ ¸ÀAWÀ f¯Áè¢üPÁjUÀ¼À PÀbÉÃj PÉ.f.gÀ¸ÉÛ, ¨ÉAUÀ¼ÀÆgÀÄ | 15 | Completed | Nirmithi Kendra | 15 | 0
27 | ¸ÀÁªÀðd¤PÀ ±ËZÁ®AiÀÄ ¤ªÀiÁðt & ¸ÉÆÃ¯Ágï ¯ÉÊmï ªÀÄvÀÄÛ ¤ÃgÀÄ ¸ÀgÀ§gÁdÄ, ¸ÁªÀðd¤PÀgÀÄ PÀÄ½vÀÄPÉÆ¼ÀÄîªÀ PÀÄað, PÉ®ªÀÅ ¨sÁUÀUÀ¼À°è PÁAQæÃmï ªÀÄvÀÄÛ EvÀgÉ j¥ÉÃj PÉ®¸ÀUÀ¼ÀÄ a£Àß¥Àà GzÁå£ÀªÀ£À ªÁqïð £ÀA,99 gÁeÁf£ÀUÀgÀ | 10 | Completed | Nirmithi Kendra | 10 | 0
28 | Re-Troffing of Essential life line Building to Government Boys Model School, Chamarajpet ward NO.140, Chamarajpet | 12 | Completed | EEPRED | 12 | 0
29 | Construction of Library block at ward No.141, Kasturibanagar Bangalore-18 | 12.5 | Completed | EEPRED | 12.5 | 0
30 | Development of Dhobi Ghat including water tank and other accessories at ward No.107, Shivanagar Bangalore-10 | 15 | Completed | EEPRED | 15 | 0
31 | Development of Park near Dhobi Ghat including children play equipment, light and watchman shed and toilet at ward No.107, Shivangara, Bangalore-10. | 10 | Completed | EEPRED | 10 | 0
32 | ±ËZÁ®AiÀÄ ªÀÄvÀÄÛ ¨sÀzÀævÁ PÉÆoÀrUÉ ²æÃ gÁªÀÄ ªÀÄA¢gÀ ªÁqïð £ÀA.108gÀ §Æån ¸Áàmï GzÁå£ÀªÀ£ÀzÀ°è | 10 | Under Progress | Nirmithi Kendra | 5 | 5
33 | ±Á¯Á PÉÆoÀr ºÁUÀÆ UÀæAxÁ®AiÀÄ ¤ªÀiÁðt PÉÊgÉ° ¤PÉÃvÀ£ï JdÄPÉÃµÀ£ï læ¸ïÖ, EA¢gÁ£ÀUÀgÀ, ¨ÉAUÀ¼ÀÆgÀÄ | 25 | Completed | EEPRED | 25 | 0 |  |  | ¨ÁåAPï EAlgÉ¸ïÖ zÀÄrØ£À°è PÉÆqÀ¯ÁVzÉ
| 2% Administrative Expenses | 10 | Under Progress |  | 0 | 10
| MlÄÖ | 530.39 | 34 | 33 | 390.39 | 140
Abstract
| Total Work Issued | 33 | 520.39
| Completed Works | 30 | 385.39
| Pending | 3 | 135

## Sheet8 (hidden)
1 | qÉ¸ïÌ ¸Àè¨ï gÀ¸ÉÛ C¼ÀªÀr¸ÀÄªÀ PÀÄjvÀÄ:- ¸ÀªÀðdÕ£ÀUÀgÀ ªÁqïð £ÀA.79 PÉÆªÀÄ¯ï ºÉÆÃmÉ¯ï ªÀÄÄA¨sÁUÀzÀ°è ªÀÄÄRågÀ¸ÉÛ PÀPïìmË£ï | 50 | Completed | EEPRED | 50